## Slide 1
North Sound Terminal — Ramp NS-2 Value Engineering Decision
Board decision artifact — independent senior civil engineer review
Project: WSDOT Marine Project NS-27-041, Island County — 162-ft movable steel vehicle-transfer ramp
Memo basis: North_Sound_Terminal_Project_Memo.docx (E. Park, P.E., 2027-03-18), §1–§5
DECISION REQUESTED: fix the defensible base scope and set the VE disposition for the
overlay/FRP alternative versus full steel deck-panel replacement, October 2027 – February 2028 construction.
Evidence posture: all submitted estimates, annotations and assertions are treated as CLAIMS, not approvals.
Quantities, costs, evidence states and recommendation are identical to quantity_cost_decision_model.xlsx.
Prepared 2026-08-24. Companion workbook: quantity_cost_decision_model.xlsx (auditable calculation record).

## Slide 2
Scope, Geometry and Governing References
What is fixed, what is claimed, what governs
Asset fact | Value | Source locator
Asset / movable length | Ramp NS-2, 162.0 ft hinge-to-vessel | ferry_ramp_dimensions…csv "Total movable length"
Panel groups / takeoff segments | 12 groups; 48 takeoff segments | same file; ramp_segment_takeoff.csv RMP-001…048
Nominal roadway width | 31.5 ft (segment clear widths 19.44–25.11 ft) | dimensions file; takeoff cols C
Skew | max 41° (survey basis); hinges N 27° / S 33° | dimensions file rows "Maximum skew", "Hinge"
Plate thickness | nominal 0.375 in; grid reading 0.31 in SUBMITTED | dimensions file; ledger FEE-001/009/017
Authorized scope | panels, wearing surface, 2 skewed hinge joints, bearings, corrosion, coating, drainage, traffic, environmental, commissioning, optional FRP | Memo §1
Operational floor | ≥1 ramp active except approved overnight windows | Memo §4; dimensions file "Minimum active ramps"
Governing references applied
  WSDOT BDM Ch.12 (M 23-50.24, Jun 2025): quantity computation ±1% final accuracy (12.2.4, PDF p.7); unit-cost appendices 12.3-A1…A4 (PDF pp.33–37)
  WSDOT Cost Estimating Manual M 30-34.04 (Feb 2026): DBB change-order contingency 4% (§14.19, PDF p.86); mobilization bands (Exh.14-5); BOE duties (§6.04)
  WSDOT Std Specs M 41-10 (2025): 1-09 measurement/payment principles; 6-03 structural steel; 6-02 joints; 6-07.3(12) ferry-terminal painting; 6-21/6-22 overlays
  FHWA VE policy (FHWA-HIF-24-080): VE must confirm needed functions and life-cycle cost (23 U.S.C. 106(f)(2), p.1); $40M bridge threshold not met — board-directed review
  FRED PPI PCU327320327320 (ready-mix concrete) — escalation proxy only; no steel/fabrication index supplied

## Slide 3
Quantity Discipline — Four Quantities, Kept Separate
Memo §2: physical, spec-payable, technician, quoted must not be conflated
Item family | Physical (recomputed) | Spec-payable (clause) | Technician / vendor schedule | Bid (quoted)
Panel removal (SF) | 3,978.59 (Σ L×W) | 3,977.6 @0.1 SF (FMR-001) | 3,877.2 | 3,980
New steel panels (SF) | 3,978.59 | 3,980 whole SF (FMR-002) | 3,877.2 | 3,980
Hinge/joint seals (LF) | 1,255.33 skew-true | 1,255.6 @0.1 LF (FMR-004) | 1,069.2 (skew ignored) | 1,260
Wearing overlay (SF, VE) | 3,978.59 | 3,980 whole SF (FMR-003) | 3,980 | 3,980
Corrosion repair (SF) | 169.02 mapped | 170 whole SF (FMR-006) | 780 (unverified) | 820
Bearings (EA) | 24 | 24 (FMR-005) | 24 | 24
Coating + containment (SF) | 5,240 | 5,240 DFT-passing only (FMR-007) | 5,240 | 5,240
FRP zones (SF, VE) | 1,360 max boundary | 1,360 after qualification | 1,360 | 1,360
Reading: bid panel quantities match recomputed plan geometry within 0.1% — the base bid is dimensionally honest; vendor per-segment schedule (3,877.2 SF) is not the pay basis.
Corrosion is the live quantity conflict: mapped 170 SF vs technician 780 SF vs bid 820 SF — payable is mapped only; the rest is a named risk allowance, not scope.
Joint payable length uses geometric skew (W/cos θ) per FMR-004; the vendor schedule under-measures by 15% by ignoring skew.

## Slide 4
Segment Takeoff Findings
Independent recomputation of ramp_segment_takeoff.csv (48 segments)
Boundary U1 — coverage: Σ segment lengths = 178.2 ft vs stated movable length 162.0 ft (+9.1%). Payable quantities carry the full takeoff; if the 162-ft movable limit governs, panel/joint scope reduces ~9.1%. Confirm before PS&E.
Boundary U2 — joint scope: takeoff joint network = 1,255.3 LF skew-true (matches bid 1,260 LF) but the two-hinge geometry is only 71.8 LF (N: 30.8 ft @ 27°; S: 31.2 ft @ 33°). Which network is in scope is unresolved; quantities carry the 48-segment network.
Verification mix: 16 verified / 16 submitted / 16 field-check-required segments. BDM 12.2.4 requires ±1% final quantity accuracy — the 32 non-verified segments must be field-checked before final contract quantities.
In-plan skew does not inflate panel plate surface (parallelogram area = L × clear width); it DOES lengthen joints (W/cos θ). The bid got both right; the vendor schedule got both wrong.
Locator: Segment_Takeoff sheet rows 5–52 with per-segment formulas; totals row 53; variance column O isolates per-segment vendor-schedule overstatement.

## Slide 5
Measurement & Payment Clauses — What They Do to the Money
ferry_measurement_payment_rules.csv FMR-001…012 + WSDOT Std Spec 1-09
Clause | Pay basis | Effect on this project
FMR-001/002 panels | accepted removed / installed surface | Vendor schedule quantities excluded; pay = 3,977.6 / 3,980 SF
FMR-004 hinge joint | geometric skew length, 0.1 LF | Pay 1,255.6 LF; vendor 1,069.2 LF non-payable as documented
FMR-006 corrosion | mapped steel-loss area only | Unmapped steel excluded → 170 SF payable; 780 SF is allowance
FMR-007 coating | DFT-passing surface | 5,240 SF "not payable until accepted"; adhesion claim contradicted
FMR-005 bearings | verified zone, whole EA | Unverified adjacent damage excluded → A01 NDE is the hedge
FMR-009/010 LS & staging | accepted contract basis / approved stage plan | Unapproved service outage non-payable; closure approval is a gate
FMR-012 risk allowance | board-approved risk basis | Allowances (B06, V04, V07, A02) need named-risk documentation
Std Spec 1-09.3 (book p.1-128, PDF p.180): unit prices are full payment "in place"; no double payment across items. 1-09.1: no measurement for rejected work or work outside plan lines.
Std Spec 6-07.5 (PDF p.564): coating progress payments only for area "satisfactorily cleaned and coated" — consistent with FMR-007 DFT-passing basis.

## Slide 6
Technical / Evidence Gate Matrix
ferry_engineering_evidence_ledger.csv — 24 rows = 8 gates × 3 identical repeats (counted once, not thrice)
Gate | Domain | Observed | State | Decision impact
G1 | Steel thickness | 0.31 in | SUBMITTED | If verified low, VE substrate fails → base forced
G2 | Corrosion loss | 18% UT | VERIFIED | ≈716 SF deck-wide — supports technician 780 SF over mapped 170 SF
G3 | Coating adhesion | 680 psi | CONTRADICTED | Overlay bond + coating acceptance unreliable until resolved
G4 | Chlorides | 6.8 µg/cm² | FIELD-VERIFY | Drives prep level and overlay bond risk
G5 | Hinge geometry | 27° skew | SUBMITTED | Joint pay basis; boundary U2
G6 | Bearings | conditional | VERIFIED | B04 scope conditional → accept A01 NDE
G7 | Tidal closure | 6 hr/night | CONTRADICTED | VE staging feasibility; A02 deferred
G8 | FRP qualification | vendor submittal | FIELD-VERIFY | Condition precedent to VE award (23 U.S.C. 106(f)(2) function test)
Five of eight gates are not decision-grade: 2 contradicted, 2 field-verification-required, 1 submitted-only. Only corrosion loss and bearing condition are independently verified.

## Slide 7
Submitted Estimates — Internally Consistent, Externally Unverified
ferry_base_ve_bid_items.csv (estimate dates 2027-02-15 base / 2027-04-01 VE)
Option | Submitted total | Composition flags
Base — full replacement (B01–B07) | $5,930,700 | B01 removal and B06 staging are "allowance" scope_status, not firm
VE — overlay/FRP (V01–V07) | $2,959,140 | V04 seals and V07 qualification carry allowance/qualification risk
Add alternates (A01–A02) | $331,200 | A02 is allowance pending operations confirmation
Submitted VE saving claim | $2,971,560 (50.1%) | Arithmetic checks: every qty × unit = stated amount (Δ = 0)
All 17 line items recompute exactly (Submitted_Bids sheet, Δ column = 0). Internal consistency ≠ accuracy: quantities and prices remain submitted_unverified.
Bid quantities use plan geometry for panels (correct) and skew-true length for joints (correct) — but corrosion (820 SF) exceeds mapped extent by 4.8× without evidence.
Mobilization B07 $525,000 = 9.7% of base work — inside CEM Exh.14-5 band (8–10% for $5–10M contracts), though bundled "submitted allowances" need breakdown per CEM §10.07.

## Slide 8
Market & Escalation Evidence
WSDOT benchmark ranges vs submitted unit prices
Item | Submitted | Benchmark (locator) | Assessment
B02 orthotropic panels $/SF | 615 | Carbon steel $2.75–3.75/LB (BDM App.12.3-A3, p.35) | No comparable benchmark — UNVALIDATED
B05 coating+containment $/SF | 128 | Painting existing steel $15–45/SF (BDM App.12.3-A4, p.37) | ABOVE range; ferry-terminal Class-1 containment (Std Spec 6-07.3(12)) is onerous — premium UNVALIDATED
B03 hinge seals $/LF | 840 | Strip seal $450–900/LF (BDM p.36) | Within range
V04 seal rehab $/LF | 515 | Strip seal $450–900/LF (BDM p.36) | Within range (low end)
V05 corrosion repair $/SF | 246 | Bridge deck repair $150–350/SF (BDM p.37) | Within range (proxy only)
V03 wearing overlay $/SF | 174 | Mod. conc. overlay $35–50/CF, $40–75/SY (BDM p.36) | Different system — UNVALIDATED
Escalation | +2.18%/yr | FRED PPI PCU327320327320, 2025-07→2026-07 | Concrete index proxy; steel index not supplied
WSDOT 2025 bid history (33 contracts, Jan–Jun 2025): median low bid −4.3% vs engineer estimate (21/33 under). Only comparable marine contract: Bremerton Ferry Terminal steel dolphin replacement (p.6, XE3589, est $3.09M, low bid $2.87M = −7.0%, 4 bidders). No orthotropic/FRP/ramp items — specialty prices unvalidated.
Consequence: ~$3.9M of the $5.9M base (panels + coating) and ~$1.4M of VE (FRP + overlay) prices rest on unvalidated submitted pricing. Independent totals inherit this risk — stated, not hidden.

## Slide 9
Independent Estimate & Zero-Residual Bridge
Payable quantities × submitted price basis + escalation + 4% DBB contingency (CEM §14.19)
Walk component | Base ($) | VE ($)
Submitted total | 5,930,700 | 2,959,140
Panel removal qty → 3,977.6 SF (FMR-001) | −230 | 0
Joint length → 1,255.6 LF (FMR-004) | −3,696 | −2,266
Corrosion → mapped 170 SF (FMR-006) | 0 | −159,900
Named risk allowance: corrosion to 780 SF (FMR-012) | 0 | +150,060
Price-basis adjustment (none — no independent pricing supplied) | 0 | 0
Escalation to midpoint (+2.18%/yr × 0.85 yr) | +109,645 | +54,520
Change-order contingency 4% | +241,457 | +120,062
INDEPENDENT TOTAL (residual = 0) | 6,277,875 | 3,121,616
Independent VE advantage: $3,156,259 first cost — LARGER than the submitted claim ($2,971,560) because the base bid carries more unfounded quantity than the VE bid.
Excluded per BDM 12.3.3: sales tax, PE/CE engineering; program level adds per CEM Exh.7-3/7-5. Bridge sheet residual formulas evaluate to exactly 0.

## Slide 10
Lifecycle Present Worth — 40-Year Horizon
Parameters: 3% real discount (2–4% tested); VE renewal = full scope repeat at yr 22
Measure | Base replacement | VE overlay/FRP
Initial independent total (YOE $) | 6,277,875 | 3,121,616
Service life basis | 40 yr (planning assumption) | 22 yr CLAIMED, unverified (P06)
Renewal PW | 0 | +1,629,148 at yr 22
Lifecycle PW total | 6,277,875 | 4,750,764
VE lifecycle advantage | — | $1,527,111
At 2% / 4% real | advantage holds | holds at both bounds
VE is PW-preferred even with a full-scope renewal at year 22, because the VE initial price is ~50% of base. Cost arithmetic does not decide this — evidence does.
Symmetrical exclusions: routine maintenance and residual value not supplied for either option; base-option overlay renewals within 40 yr not modelled (not supplied).
Locator: Lifecycle sheet rows 5–12; sensitivity rows 16–18; Recommendation figure cells link to Lifecycle!B12/C12.

## Slide 11
Decision Switches — What Would Change the Answer
Sensitivity_Switch sheet; all formulas live
Switch | Threshold | Disposition if triggered
Verified VE system life | ≤ 16 yr → 2nd renewal inside 40 yr erases PW advantage (at 16 yr: −$1,268) | REVERT to base replacement
FRP qualification (G8) | fails field verification | REVERT — function cannot be confirmed
Steel thickness (G1) | verified < 0.31 in submitted grid | REVERT — overlay substrate inadequate
Adhesion / chlorides (G3/G4) | contradiction unresolved or over threshold | REVERT or re-price prep scope
Closure windows (G7) | ≥6-hr nights not confirmed in writing | VE staging infeasible as priced; A02 ($52k/window) or REVERT
Corrosion extent (cost only) | breakeven ≈ 12,800 SF > deck area 3,978.6 SF | Cannot flip arithmetically; matters via substrate adequacy (G1/G2)
Checked non-switches: quantity corrections (<0.4% of totals), discount rate 2–4%, mobilization band position — none move the ranking.

## Slide 12
Operational & Environmental Constraints
Hard constraints that bound both options
Service floor: at least one vehicle-transfer ramp active at all times except approved overnight windows (Memo §4; dimensions "Minimum active ramps" = 1).
Night closure maximum 6 hr — CONTRADICTED evidence (FEE-007/015/023). Until operations confirms windows in writing, VE overlay cure/staging is unschedulable as priced; A02 deferred.
Environmental: containment required for coating/removal (dimensions "Containment: required"). Std Spec 6-07.3(10)A SSPC Guide 6 Class 1 full enclosure; waste testing/disposal per 6-07.3(10)F (TCLP, WAC 173-303); FMR-011 excludes penalties/rework from payment.
Season: construction Oct 2027–Feb 2028 matches the marine work window (CEM §10.09: marine peak Nov–Mar, PDF p.51) — advertise several months ahead.
Std Spec 2-02.3(2)A1: bridge demolition plan (Type 2E working drawing) with containment/debris control required for panel removal — include in staging conditions.

## Slide 13
Recommendation
Defensible base scope + conditional VE disposition + decision-changing conditions
R1 — BASE SCOPE (decision floor): full replacement at payable quantities — remove 3,977.6 SF; new panels 3,980 SF; joint seals 1,255.6 LF; bearings 24 EA; coating 5,240 SF DFT-passing. Independent total $6,277,875 (YOE, incl. escalation + 4% COC).
R2 — VE DISPOSITION: CONDITIONAL APPROVAL. Overlay/FRP at $3,121,616 independent (first-cost advantage $3,156,259; 40-yr PW advantage $1,527,111) is approvable ONLY after gates G1–G8 actions complete and verified system life > 16 yr. Any failure of G1/G3/G4/G7/G8 → revert to R1.
R3 — ADD-ALTERNATES: accept A01 expanded bearing NDE ($175,200) now; defer A02 closure windows ($156,000 allowance) pending written operations confirmation.
R4 — UNRESOLVED BOUNDARIES (stated, not fabricated): U1 takeoff 178.2 ft vs movable 162.0 ft; U2 joint network 1,255.3 LF vs two-hinge 71.8 LF; U3 corrosion 170/780/820 SF; U4 unvalidated panel/coating/FRP/overlay prices; U5 concrete-PPI escalation proxy; U6 assumed 3% discount rate.
Process: recompute to ±1% before PS&E (BDM 12.2.4); BOE documentation per CEM §6.04; VE per FHWA practice (FHWA-HIF-24-080) — federal $40M threshold not triggered; this is a board-directed review.