## README
North Sound Terminal — Ramp NS-2 Value Engineering Decision Model
Independent senior civil engineer audit record ¦ prepared 2026-08-24 ¦ accompanies ferry_terminal_ve_board.pptx
PURPOSE: Auditable calculation record supporting the VE board decision on the North Sound vehicle-transfer ramp (Ramp NS-2),
WSDOT Marine Project NS-27-041, Island County (memo: North_Sound_Terminal_Project_Memo.docx, §1–§5).
METHOD: Physical surface area, specification-payable quantity, technician estimate, and vendor-quoted quantity are computed
and carried SEPARATELY (memo §2). Payment quantities follow the supplied measurement clauses (ferry_measurement_payment_rules.csv,
FMR-001…FMR-012) which require field-verified accepted quantities, not vendor schedule quantities. Unit prices are SUBMITTED prices
(estimate dates 2027-02-15 / 2027-04-01) and are treated as unverified evidence claims, benchmarked where WSDOT references allow.
SHEET MAP:
Parameters ............ global assumptions (discount rate, escalation, contingency) — all downstream sheets reference these cells
Segment_Takeoff ....... 48-segment geometry recomputation with payable-quantity rounding per FMR clauses
Quantity_Reconciliation physical vs payable vs technician vs submitted/vendor, per item family, with locators
Submitted_Bids ........ submitted bid items, internal consistency check (qty × unit price vs stated amount)
Market_Evidence ....... WSDOT/BDM/CEM benchmark ranges and PPI escalation evidence vs submitted unit prices
Independent_Estimate .. engineer common-scope estimate for both options on payable quantities + markups
Bridge_Zero_Residual .. submitted-to-independent reconciliation walk; residual formula must equal 0
Evidence_Gates ........ technical/evidence gate matrix (8 gates) with decision impact
Lifecycle ............. 40-yr present-worth comparison, base replacement vs overlay/FRP VE
Sensitivity_Switch .... joint cost/evidence switch: decision-changing conditions and breakevens
Recommendation ........ dispositions, conditions precedent, unresolved boundaries
COLOR KEY: yellow = input/assumption (auditable, changeable); green = formula; red = flag/unresolved boundary.
KEY UNRESOLVED BOUNDARIES (see Recommendation sheet): (1) takeoff length 178.2 ft vs stated movable length 162.0 ft;
(2) bid joint scope 1,260 LF vs two-hinge geometry 71.8 LF vs 48-segment joint network 1,255.3 LF;
(3) corrosion extent: mapped 170 SF vs technician 780 SF vs bid 820 SF; (4) FRP qualification and 22-yr life are submitted, unverified;
(5) 6-hr night closure is contradicted by operations evidence; (6) coating adhesion test contradicted.

## Parameters
Global Parameters & Assumptions
Yellow cells are the only manual inputs; all downstream sheets reference this page.
Ref | Parameter | Value | Unit | Basis / locator
P01 | Real discount rate for lifecycle PW | 0.03 | per yr | Assumption (no agency rate supplied); sensitivity 2%–4% on Lifecycle sheet
P02 | Escalation rate, estimate date to construction midpoint | 0.0218 | per yr | FRED PPI ready-mix PCU327320327320: 2025-07=393.322 to 2026-07=401.896 = +2.18%/yr (fred_ppi_ready_mix_concrete.csv rows 2025-07/2026-07); latest available observation 2026-07; proxy only — steel/fabrication index not supplied
P03 | Years from estimate date (2027-02-15 base / 2027-04-01 VE) to construction midpoint (~2027-12) | 0.85 | yr | Memo §4: construction Oct 2027–Feb 2028; midpoint 2027-12
P04 | Change-order contingency (design-bid-build) | 0.04 | fraction | WSDOT Cost Estimating Manual M 30-34.04 §14.19 (PDF p.86): DBB COC = 4%
P05 | Design/scope allowance on evidence-open quantities | 0.1 | fraction | BDM 12.3.3.A.2 (PDF p.15): minimum 10% contingency to cover scope creep; CEM Exhibit 7-3 (PDF p.39): design phase misc allowance 10–20%
P06 | Overlay/FRP VE claimed service life | 22 | yr | ferry_ramp_dimensions_and_technician_quantities.csv row "Lifecycle, Overlay/FRP VE, Claimed life, 22, years, submitted; verify" — SUBMITTED, UNVERIFIED
P07 | Base replacement analysis life | 40 | yr | Same file, row "Lifecycle, Base replacement, Analysis life, 40, years, planning assumption"
P08 | VE renewal cost as fraction of initial VE independent estimate | 1 | fraction | Assumption: full repeat of VE scope at renewal (conservative); sensitivity on Lifecycle sheet
P09 | Night closure maximum (submitted, contradicted) | 6 | hr/night | ferry_engineering_evidence_ledger.csv FEE-007/015/023 tidal closure 6 h, evidence_state=contradicted; dimensions file "Night closure, Maximum duration, 6, hours, requires operations approval"
P10 | Corrosion risk allowance upper basis | 780 | SF | Technician estimate, dimensions file row "Corrosion, Mapped repair, Technician estimate, 780, SF, unverified submitted quantity" — carried as risk allowance only, NOT payable quantity

## Segment_Takeoff
Segment Takeoff — Independent Recomputation
Source rows: ramp_segment_takeoff.csv RMP-001…RMP-048 (verbatim geometry); computed columns are formulas. Payable rounding per FMR-001/002/004/006.
Segment | Length (ft) | Clear width (ft) | Skew (deg) | Plan area = L×W (SF) | Skew joint length = W/cos(skew) (LF) | Payable removal (SF, 0.1) FMR-001 | Payable new panel (SF, whole) FMR-002 | Payable joint (LF, 0.1) FMR-004 | Submitted panel area (SF) | Submitted joint (LF) | Submitted corrosion (SF) | Payable corrosion (SF, whole) FMR-006 | Inspection record status | Variance: submitted − plan area (SF)
RMP-001 | 2.7 | 19.44 | 18 | [5 empty] | 56.16 | 19.44 | 1.31 |  | verified
RMP-002 | 3.375 | 20.574 | 27 | [5 empty] | 66.66 | 20.574 | 2.36 |  | submitted
RMP-003 | 4.05 | 21.708 | 33 | [5 empty] | 84.4 | 21.708 | 3.78 |  | field-check-required
RMP-004 | 4.725 | 22.842 | 41 | [5 empty] | 103.61 | 22.842 | 5.61 |  | verified
RMP-005 | 2.7 | 23.976 | 18 | [5 empty] | 62.15 | 23.976 | 3.95 |  | submitted
RMP-006 | 3.375 | 25.11 | 27 | [5 empty] | 81.36 | 25.11 | 2.12 |  | field-check-required
RMP-007 | 4.05 | 19.44 | 33 | [5 empty] | 84.24 | 19.44 | 2.68 |  | verified
RMP-008 | 4.725 | 20.574 | 41 | [5 empty] | 93.32 | 20.574 | 4.18 |  | submitted
RMP-009 | 2.7 | 21.708 | 18 | [5 empty] | 56.27 | 21.708 | 3.05 |  | field-check-required
RMP-010 | 3.375 | 22.842 | 27 | [5 empty] | 74.01 | 22.842 | 4.7 |  | verified
RMP-011 | 4.05 | 23.976 | 33 | [5 empty] | 93.22 | 23.976 | 2.43 |  | submitted
RMP-012 | 4.725 | 25.11 | 41 | [5 empty] | 113.9 | 25.11 | 4.03 |  | field-check-required
RMP-013 | 2.7 | 19.44 | 18 | [5 empty] | 56.16 | 19.44 | 2.26 |  | verified
RMP-014 | 3.375 | 20.574 | 27 | [5 empty] | 66.66 | 20.574 | 3.61 |  | submitted
RMP-015 | 4.05 | 21.708 | 33 | [5 empty] | 84.4 | 21.708 | 5.36 |  | field-check-required
RMP-016 | 4.725 | 22.842 | 41 | [5 empty] | 103.61 | 22.842 | 2.7 |  | verified
RMP-017 | 2.7 | 23.976 | 18 | [5 empty] | 62.15 | 23.976 | 2.2 |  | submitted
RMP-018 | 3.375 | 25.11 | 27 | [5 empty] | 81.36 | 25.11 | 3.64 |  | field-check-required
RMP-019 | 4.05 | 19.44 | 33 | [5 empty] | 84.24 | 19.44 | 4.09 |  | verified
RMP-020 | 4.725 | 20.574 | 41 | [5 empty] | 93.32 | 20.574 | 5.93 |  | submitted
RMP-021 | 2.7 | 21.708 | 18 | [5 empty] | 56.27 | 21.708 | 1.47 |  | field-check-required
RMP-022 | 3.375 | 22.842 | 27 | [5 empty] | 74.01 | 22.842 | 2.62 |  | verified
RMP-023 | 4.05 | 23.976 | 33 | [5 empty] | 93.22 | 23.976 | 4.18 |  | submitted
RMP-024 | 4.725 | 25.11 | 41 | [5 empty] | 113.9 | 25.11 | 6.17 |  | field-check-required
RMP-025 | 2.7 | 19.44 | 18 | [5 empty] | 56.16 | 19.44 | 3.2 |  | verified
RMP-026 | 3.375 | 20.574 | 27 | [5 empty] | 66.66 | 20.574 | 1.74 |  | submitted
RMP-027 | 4.05 | 21.708 | 33 | [5 empty] | 84.4 | 21.708 | 2.99 |  | field-check-required
RMP-028 | 4.725 | 22.842 | 41 | [5 empty] | 103.61 | 22.842 | 4.64 |  | verified
RMP-029 | 2.7 | 23.976 | 18 | [5 empty] | 62.15 | 23.976 | 3.37 |  | submitted
RMP-030 | 3.375 | 25.11 | 27 | [5 empty] | 81.36 | 25.11 | 5.17 |  | field-check-required
RMP-031 | 4.05 | 19.44 | 33 | [5 empty] | 84.24 | 19.44 | 1.97 |  | verified
RMP-032 | 4.725 | 20.574 | 41 | [5 empty] | 93.32 | 20.574 | 3.31 |  | submitted
RMP-033 | 2.7 | 21.708 | 18 | [5 empty] | 56.27 | 21.708 | 2.52 |  | field-check-required
RMP-034 | 3.375 | 22.842 | 27 | [5 empty] | 74.01 | 22.842 | 4.01 |  | verified
RMP-035 | 4.05 | 23.976 | 33 | [5 empty] | 93.22 | 23.976 | 5.92 |  | submitted
RMP-036 | 4.725 | 25.11 | 41 | [5 empty] | 113.9 | 25.11 | 2.97 |  | field-check-required
RMP-037 | 2.7 | 19.44 | 18 | [5 empty] | 56.16 | 19.44 | 1.78 |  | verified
RMP-038 | 3.375 | 20.574 | 27 | [5 empty] | 66.66 | 20.574 | 2.99 |  | submitted
RMP-039 | 4.05 | 21.708 | 33 | [5 empty] | 84.4 | 21.708 | 4.57 |  | field-check-required
RMP-040 | 4.725 | 22.842 | 41 | [5 empty] | 103.61 | 22.842 | 6.58 |  | verified
RMP-041 | 2.7 | 23.976 | 18 | [5 empty] | 62.15 | 23.976 | 1.62 |  | submitted
RMP-042 | 3.375 | 25.11 | 27 | [5 empty] | 81.36 | 25.11 | 2.88 |  | field-check-required
RMP-043 | 4.05 | 19.44 | 33 | [5 empty] | 84.24 | 19.44 | 3.39 |  | verified
RMP-044 | 4.725 | 20.574 | 41 | [5 empty] | 93.32 | 20.574 | 5.06 |  | submitted
RMP-045 | 2.7 | 21.708 | 18 | [5 empty] | 56.27 | 21.708 | 3.58 |  | field-check-required
RMP-046 | 3.375 | 22.842 | 27 | [5 empty] | 74.01 | 22.842 | 1.93 |  | verified
RMP-047 | 4.05 | 23.976 | 33 | [5 empty] | 93.22 | 23.976 | 3.3 |  | submitted
RMP-048 | 4.725 | 25.11 | 41 | [5 empty] | 113.9 | 25.11 | 5.1 |  | field-check-required
TOTALS
Row check: Σ length = 178.2 ft vs stated movable length 162.0 ft (ferry_ramp_dimensions…csv "Total movable length") — UNRESOLVED BOUNDARY U1: takeoff covers ~9.1% more length than the movable span; see Recommendation.
Joint scope check: Σ geometric skew joint length 1,255.3 LF vs bid items B03/V04 = 1,260 LF (consistent); but two-hinge geometry (N 30.8 ft @27°, S 31.2 ft @33°) = 71.8 LF — UNRESOLVED BOUNDARY U2: whether payable joint scope is the 48-segment joint network or only two hinges.
Payable basis: panel surface = plan (L×W) area — skew is in-plan; panel plate surface is not increased by skew angle. Joint length across a skewed joint = clear width / cos(skew) per FMR-004 "geometric skew length".
Corrosion payable shown as mapped takeoff (rounded whole SF per FMR-006); technician estimate 780 SF is unverified and carried as risk allowance (P10), not as payable quantity.
Verification mix: 16 verified / 16 submitted / 16 field-check-required segments (column N); quantities from non-verified segments remain conditional per memo §2.

## Quantity_Reconciliation
Quantity Reconciliation — physical vs payable vs technician vs submitted
Physical and payable columns are formulas from Segment_Takeoff totals; technician/submitted columns cite source rows.
Item family | Physical computed | Payable (spec) | Technician / submitted claim | Bid quantity | Variance: bid − payable | Payable basis (clause) | Evidence state | Locator
Steel panel removal (SF) |  |  | 3877.2 | 3980 |  | geometry verified; vendor schedule differs | ramp_segment_takeoff.csv Σ; ferry_base_ve_bid_items.csv B01; FMR-001
New steel deck panels (SF) |  |  | 3877.2 | 3980 |  | geometry verified; vendor schedule differs | ramp_segment_takeoff.csv Σ; ferry_base_ve_bid_items.csv B02; FMR-002
Skewed hinge/joint seals (LF) |  |  | 1069.2 | 1260 |  | submitted joint = clear width (skew ignored) | ramp_segment_takeoff.csv Σ; ferry_base_ve_bid_items.csv B03/V04; FMR-004; U2 unresolved
Wearing overlay (SF, VE option) |  |  | 3980 | 3980 |  | submitted = plan area (consistent) | ferry_base_ve_bid_items.csv V03; FMR-003
Corrosion repair (SF) | 169.02 |  | 780 | 820 |  | CONFLICT: mapped 170 / technician 780 / bid 820 | ferry_ramp_dimensions…csv corrosion row; ferry_base_ve_bid_items.csv V05; FMR-006
Bearing interface zones (EA) | 24 | 24 | 24 | 24 |  | count consistent; condition "conditional" per FEE-006 | ferry_ramp_dimensions…csv bearings row; ferry_base_ve_bid_items.csv B04; FMR-005
Coating / containment (SF) | 5240 | 5240 | 5240 | 5240 |  | area consistent; adhesion 680 psi CONTRADICTED (FEE-003) | ferry_ramp_dimensions…csv coating row "not payable until accepted"; ferry_base_ve_bid_items.csv B05; FMR-007
FRP panel zones (SF, VE option) | 1360 | 1360 | 1360 | 1360 |  | FRP qualification FIELD-VERIFICATION-REQUIRED (FEE-008) | ferry_ramp_dimensions…csv FRP row; ferry_base_ve_bid_items.csv V01/V02

## Submitted_Bids
Submitted Bid Items — Internal Consistency Check
Source: ferry_base_ve_bid_items.csv (all rows, evidence_status=submitted_unverified). Amount check = qty × unit price vs submitted amount.
Option | Item | Description | Qty | Unit | Unit price ($) | Submitted amount ($) | Recomputed amount ($) | Δ ($) | Scope status | Estimate date
base_full_replacement | B01 | Remove existing steel deck panels | 3980 | SF | 96 | 382080 |  |  | allowance | 2027-02-15
base_full_replacement | B02 | Fabricate and install orthotropic steel panels | 3980 | SF | 615 | 2447700 |  |  | included | 2027-02-15
base_full_replacement | B03 | Replace skewed hinge seals | 1260 | LF | 840 | 1058400 |  |  | included | 2027-02-15
base_full_replacement | B04 | Bearing-interface repairs | 24 | EA | 18200 | 436800 |  |  | included | 2027-02-15
base_full_replacement | B05 | Protective coating and containment | 5240 | SF | 128 | 670720 |  |  | included | 2027-02-15
base_full_replacement | B06 | Ferry operations and traffic staging | 1 | LS | 410000 | 410000 |  |  | allowance | 2027-02-15
base_full_replacement | B07 | Mobilization and submitted allowances | 1 | LS | 525000 | 525000 |  |  | included | 2027-02-15
ve_overlay_frp | V01 | Selective panel removal | 1360 | SF | 112 | 152320 |  |  | included | 2027-04-01
ve_overlay_frp | V02 | Install qualified FRP panel zones | 1360 | SF | 488 | 663680 |  |  | included | 2027-04-01
ve_overlay_frp | V03 | Prepare and install wearing overlay | 3980 | SF | 174 | 692520 |  |  | included | 2027-04-01
ve_overlay_frp | V04 | Rehabilitate skewed hinge seals | 1260 | LF | 515 | 648900 |  |  | allowance | 2027-04-01
ve_overlay_frp | V05 | Localized corrosion and bearing repair | 820 | SF | 246 | 201720 |  |  | included | 2027-04-01
ve_overlay_frp | V06 | Ferry operations and traffic staging | 1 | LS | 315000 | 315000 |  |  | included | 2027-04-01
ve_overlay_frp | V07 | Qualification testing and submitted allowance | 1 | LS | 285000 | 285000 |  |  | included | 2027-04-01
add_alternate | A01 | Expanded bearing NDE and contingent repair | 12 | EA | 14600 | 175200 |  |  | included | 2027-04-01
add_alternate | A02 | Additional overnight closure window | 3 | EA | 52000 | 156000 |  |  | allowance | 2027-04-01
TOTAL base_full_replacement (B01–B07)
TOTAL ve_overlay_frp (V01–V07)
TOTAL add_alternate (A01–A02)
All amounts are internally consistent (Δ = 0 expected). Items flagged "allowance" are not firm quantities/prices — they are submitted placeholders requiring board-approved basis per FMR-012 (risk) and FMR-009/010 (LS items).

## Market_Evidence
Market & Price-Basis Evidence vs Submitted Unit Prices
Benchmarks are governing-reference ranges; submitted prices are unverified claims (ferry_base_ve_bid_items.csv, evidence_status=submitted_unverified).
Item | Submitted unit price | Benchmark range | Benchmark basis / locator | Assessment
B02 Fabricate+install orthotropic steel panels ($/SF) | 615 | Structural carbon steel $2.75–3.75/LB (≈$42–57/SF plate material at 0.375 in, 15.3 lb/SF) | WSDOT BDM Ch.12 App. 12.3-A3 (PDF p.35); steel weight 490 lb/ft³ per Std Spec 6-03.5 (PDF p.515) | NOT COMPARABLE to material index — price includes fabrication, orthotropic details, install; no direct supplied benchmark. UNVALIDATED — retain price risk.
B05 Protective coating + containment ($/SF) | 128 | Painting existing steel bridges $15–45/SF | WSDOT BDM Ch.12 App. 12.3-A4 (PDF p.37) | ABOVE supplied range; ferry-terminal SSPC Guide 6 Class 1 full-removal containment (Std Spec 6-07.3(12)/(10)A, PDF pp.548,558-559) is more onerous than the generic range, but premium is UNVALIDATED — flag.
B03 Replace skewed hinge seals ($/LF) | 840 | Strip seal $450–900/LF; modular joint $500–7,000/LF | WSDOT BDM Ch.12 Superstructure Cost table (PDF p.36) | WITHIN supplied range. Plausible; still submitted_unverified.
V04 Rehabilitate skewed hinge seals ($/LF) | 515 | Strip seal $450–900/LF | WSDOT BDM Ch.12 Superstructure Cost table (PDF p.36) | WITHIN supplied range (low end). Plausible for rehab scope.
V05 Localized corrosion & bearing repair ($/SF) | 246 | Bridge deck repair $150–350/SF | WSDOT BDM Ch.12 App. 12.3-A4 (PDF p.37) | WITHIN supplied range (concrete deck repair used as proxy; steel loss repair is a different work type — treat as indicative only).
V03 Wearing overlay ($/SF) | 174 | Modified concrete overlay $35–50/CF; furnish+cure $40–75/SY | WSDOT BDM Ch.12 Superstructure Cost table (PDF p.36) | ABOVE supplied ranges; V03 is a polymer/FRP-compatible wearing surface on steel, not modified concrete — no direct supplied benchmark. UNVALIDATED — retain price risk.
B07 Mobilization + submitted allowances (LS) | 525000 | Mobilization 8–10% of contract total for $5–10M contracts | WSDOT CEM M 30-34.04 §14.17 Exhibit 14-5 (PDF p.85); BDM 12.3-A4 "Mobilization — 10%" (PDF p.37)
Escalation basis | — | PPI ready-mix concrete +2.18%/yr latest (2025-07→2026-07) | FRED PCU327320327320 (fred_ppi_ready_mix_concrete.csv, observations 2025-07=393.322, 2026-07=401.896) | Used as escalation proxy (Parameters P02). Ready-mix is a concrete index; steel/fab index not supplied — stated limitation.
WSDOT 2025 bid history | — | 33-page contract bid history, award dates Jan–Jun 2025 | wsdot_bid_history_2025.pdf (DOT_RGGB02, dated 6/13/2025) | 33 contracts, one per page pp.1-33, awards Jan-Jun 2025. Low bid vs engineer estimate: median -4.3%, mean -1.6%, 21 of 33 under (computed from report figures). ONE directly comparable marine/ferry steel contract: XE3589 SR 304 Bremerton Ferry Terminal Slip 2 Dolphin Replacements (p.6, award 03/11/2025, est $3,091,020, low bid $2,874,016 = -7.0%, 4 bidders, Kitsap). NO orthotropic-panel, FRP, or ferry-ramp bid items in the report -> specialty submitted prices remain UNVALIDATED; competitive ferry-terminal marine work is bidding ~7% under estimate.
Mobilization check: =Submitted_Bids B07 / (base total − B07):

## Independent_Estimate
Independent Engineer Estimate — common scope, payable quantities
Quantities = specification-payable (Quantity_Reconciliation); price basis = submitted unit prices (unverified, flagged); markups per Parameters.
Line | Item | Payable qty | Unit | Unit price ($) | Amount ($) | Price basis | Note
BASE OPTION — full steel deck-panel replacement
E01 | Remove existing steel deck panels |  | SF | 96 |  | submitted_unverified | Bid B01 qty 3980 → payable 3,977.6 (FMR-001)
E02 | Fabricate and install orthotropic steel panels |  | SF | 615 |  | submitted_unverified | Payable whole SF (FMR-002); price unvalidated vs BDM material index
E03 | Replace skewed hinge/joint seals |  | LF | 840 |  | submitted_unverified | Payable geometric skew length (FMR-004); U2 scope boundary flagged
E04 | Bearing-interface repairs |  | EA | 18200 |  | submitted_unverified | 24 zones; condition "conditional" per FEE-006 — see A01 alternate
E05 | Protective coating and containment |  | SF | 128 |  | submitted_unverified | Payable DFT-passing only (FMR-007); adhesion evidence contradicted (FEE-003)
E06 | Ferry operations and traffic staging (LS allowance) | 1 | LS | 410000 |  | submitted allowance | FMR-010: approved stage plans only; 6-hr closure contradicted (FEE-007)
E07 | Mobilization and submitted allowances (LS) | 1 | LS | 525000 |  | submitted_unverified | 9.7% of work items — within CEM Exh.14-5 band; breakdown required
Base construction subtotal (payable quantities)
VE OPTION — staged overlay/FRP panel concept
E08 | Selective panel removal |  | SF | 112 |  | submitted_unverified | FRP zone = submitted max boundary 1,360 SF (34.2% of deck)
E09 | Install qualified FRP panel zones |  | SF | 488 |  | submitted_unverified | CONDITION PRECEDENT: FRP qualification field verification (FEE-008)
E10 | Prepare and install wearing overlay |  | SF | 174 |  | submitted_unverified | Payable accepted finished surface (FMR-003); chloride/adhesion gates open
E11 | Rehabilitate skewed hinge/joint seals |  | LF | 515 |  | submitted allowance | Payable geometric skew length (FMR-004); submitted scope_status=allowance
E12 | Localized corrosion and bearing repair |  | SF | 246 |  | submitted_unverified | Payable = MAPPED area only (FMR-006); technician 780 SF carried as risk allowance E15
E13 | Ferry operations and traffic staging (LS) | 1 | LS | 315000 |  | submitted_unverified | FMR-010; closure window not confirmed
E14 | Qualification testing and submitted allowance (LS) | 1 | LS | 285000 |  | submitted_unverified | FMR-012: board-approved risk basis required
VE construction subtotal (payable quantities, mapped corrosion)
E15 | VE named risk allowance: corrosion extent up to technician 780 SF (P10) above mapped payable |  | SF | 246 |  | risk allowance | FMR-012 board-approved risk basis; FMR-006 excludes unmapped steel from payment until mapped
MARKUPS & TOTALS
Base subtotal
VE subtotal incl corrosion risk allowance
Escalation factor to construction midpoint (P02, P03)
Base escalated
VE escalated
Change-order contingency (P04 = 4% DBB, CEM §14.19)
BASE INDEPENDENT TOTAL (YOE $)
VE INDEPENDENT TOTAL (YOE $)
Independent savings, VE vs base (YOE $)
Submitted savings claim (Bid totals)
Scope parity: both options priced on the same payable joint length, bearing count, coating area, staging and closure constraints (memo §3 common-scope requirement).
Excluded from both totals: sales tax, PE/CE engineering, escalation beyond stated factor — per BDM 12.3.3 (PDF p.15) bridge estimates exclude these; program level must add per CEM Exhibit 7-3/7-5 (PDF pp.39,41).
Price basis limitation: no independent fabrication/marine pricing was supplied for B02, B05, V02, V03 (Market_Evidence); totals inherit submitted-price risk. This is a stated boundary, not an oversight.
Add-alternates excluded from totals: A01 $175,200 (recommended — see Recommendation), A02 $156,000 allowance (deferred pending operations confirmation).

## Bridge_Zero_Residual
Submitted → Independent Estimate Bridge (zero-residual walk)
Every dollar difference is assigned to a named component; residual formula must evaluate to 0. Memo §3 requirement.
Step | Component | Base option ($) | VE option ($) | Basis / locator
S0 | Submitted total (ferry_base_ve_bid_items.csv; estimate dates 2027-02-15 / 2027-04-01) |  |  | Submitted_Bids sheet totals
S1 | Quantity correction: panel removal to payable 3,977.6 SF (FMR-001, 0.1 SF) |  | 0 | Segment_Takeoff col G total; bid B01 = 3,980 SF
S2 | Quantity correction: hinge/joint seals to payable geometric skew length (FMR-004) |  |  | Segment_Takeoff col I total = 1,255.6 LF vs bid 1,260 LF
S3 | Quantity correction: corrosion repair to mapped payable 170 SF (FMR-006) | 0 |  | Bid V05 = 820 SF; payable = mapped takeoff only
S4 | Named risk allowance: corrosion extent to technician 780 SF (board-approved basis required, FMR-012) | 0 |  | Parameters P10; dimensions file corrosion row (unverified)
S5 | Price-basis adjustment | 0 | 0 | NONE — no independent pricing supplied; submitted prices retained as unverified basis (Market_Evidence flags)
S6 | Escalation to construction midpoint (PPI proxy +2.18%/yr × 0.85 yr) |  |  | Parameters P02/P03; FRED PCU327320327320
S7 | Change-order contingency 4% (DBB) |  |  | CEM M 30-34.04 §14.19 (PDF p.86)
INDEPENDENT TOTAL (sum of steps)
Independent_Estimate sheet total (cross-check)
RESIDUAL (must be 0)

## Evidence_Gates
Technical / Evidence Gate Matrix
8 unique gates distilled from ferry_engineering_evidence_ledger.csv (24 rows = 8 gates × 3 repeat observations, FEE-001…024). States are as-recorded; nothing upgraded without new field evidence.
Gate | Domain | Observed value | Evidence state | Ledger rows | Decision impact | Required action before reliance
G1 | Steel thickness | 0.31 in (grid) | submitted | FEE-001/009/017 | Nominal plate 0.375 in (dimensions file) → 0.31 in implies ~17% section loss; if verified low, overlay/FRP substrate adequacy fails and base replacement is forced. | Independent UT thickness survey across all 12 panel groups; acceptance limits in spec before relying on VE substrate.
G2 | Corrosion loss | 18% (UT survey) | independently-verified | FEE-002/010/018 | Only verified condition evidence. 18% of 3,978.6 SF ≈ 716 SF potential repair extent — supports technician 780 SF more than mapped 170 SF; drives VE corrosion risk allowance. | Extend UT mapping to full deck; reconcile mapped 170 SF vs 18%-extent ~716 SF before fixing V05 payable quantity.
G3 | Coating adhesion | 680 psi (pull-off) | contradicted | FEE-003/011/019 | Overcoat/overlay bond assumptions are unreliable; coating payment is DFT-passing only (FMR-007). Affects both options (base coating, VE overlay bond). | Repeat pull-off testing per accepted test plan; resolve contradiction before accepting coating/overlay scope pricing.
G4 | Chloride contamination | 6.8 µg/cm² | field-verification-required | FEE-004/012/020 | Above common coating/overlay acceptance thresholds if confirmed; drives surface-prep level and overlay bond risk in VE option. | Field chloride verification; adjust prep scope before VE overlay award.
G5 | Hinge geometry | 27° skew (field survey) | submitted | FEE-005/013/021 | Joint payable quantity is geometric skew length (FMR-004); takeoff skews 18–41° per segment. Submitted joint length (1,069 LF) ignored skew; bid 1,260 LF matches computed 1,255.3 LF. | Confirm joint network scope (boundary U2: 48-segment joints vs two hinges = 71.8 LF) and re-survey skews.
G6 | Bearing interface | conditional (visual/NDE dossier) | independently-verified | FEE-006/014/022 | Bearing repairs B04 (24 EA) rest on conditional condition; adjacent damage excluded from payment (FMR-005). Expanded NDE (A01, 12 EA, $175,200) is the prudent hedge. | Accept A01 add-alternate; complete NDE before finalizing B04 scope.
G7 | Tidal closure | 6 hr/night (ops calendar) | contradicted | FEE-007/015/023 | VE overlay cure windows and all night work assume 6-hr closures; contradiction threatens VE staging feasibility and triggers A02 closure premium ($52,000/window). Unapproved outage excluded from payment (FMR-010). | Obtain operations-approved closure windows in writing before VE award; defer A02 until then.
G8 | FRP qualification | vendor submittal: submitted | field-verification-required | FEE-008/016/024 | VE V02 ($663,680) and the 22-yr life claim rest on an unverified vendor submittal. FHWA VE doctrine: VE must confirm required functions and life-cycle cost (23 U.S.C. 106(f)(2), fhwa_ve_policy.pdf p.1) — an unqualified system cannot confirm function. | Independent qualification testing (V07 scope) with acceptance criteria fixed before award; failure reverts to base scope.
Repeat-observation note: each gate appears 3× in the ledger with identical value and state (e.g., FEE-001/009/017) — treated as one evidence record, not three independent confirmations.

## Lifecycle
Lifecycle Present-Worth Comparison (40-yr analysis horizon)
Base life 40 yr (planning assumption, P07); VE claimed life 22 yr (SUBMITTED, UNVERIFIED, P06). Real discount rate P01; renewal at P08 fraction of VE independent total. No maintenance costs supplied — exclusion stated.
Component | Base option | VE option | Note
Initial independent total (YOE $, from Independent_Estimate) |  |  | Includes escalation + 4% COC
Analysis horizon (yr) |  |  | P07
Service life before renewal (yr) |  |  | Base 40; VE 22 claimed — UNVERIFIED
Renewal events within horizon | 0 | 1 | VE renewed once at yr 22 within 40-yr horizon
Renewal cost fraction (P08) | 0 |  | Conservative: full VE scope repeat
PW of renewal ($) | 0 |  | Discounted at P01 = 3% real
LIFECYCLE PW TOTAL ($)
Lifecycle advantage of VE ($) |  |  | Positive = VE cheaper over 40 yr
Discount-rate sensitivity (PW totals, $)
Rate | Base PW | VE PW (1 renewal at claimed life) | VE PW advantage
0.02
0.03
0.04
Result is robust: VE holds a PW advantage at 2%–4% real discount even with a full-scope renewal at yr 22, because the submitted VE price is ~50% of base.
The decision therefore turns on EVIDENCE (verified life, qualification, closure windows), not on first cost — see Sensitivity_Switch.
Exclusions: routine maintenance, deck-overlay renewal of the BASE option within 40 yr, residual/salvage value — none supplied; both options treated symmetrically.

## Sensitivity_Switch
Joint Cost / Evidence Switch — decision-changing conditions
Conditions under which the recommendation flips. All cells formula-driven from Independent_Estimate and Parameters.
SWITCH 1 — Verified VE service life (the governing switch)
If the overlay/FRP system life verifies BELOW the flip value, a second renewal lands inside the 40-yr horizon and the VE PW advantage disappears.
Candidate verified life L (yr) | Renewals in 40-yr horizon | VE PW with renewals ($) | Base PW ($) | VE advantage ($) | Verdict
22
20
18
16
15
14
12
10
8
SWITCH 2 — Verified corrosion extent (VE first-cost erosion)
Verified corrosion (SF) | VE total ($) | VE advantage vs base ($) | Verdict | Note
170 |  |  |  | Mapped payable only (FMR-006)
400 |  |  |  | Intermediate
716 |  |  |  | 18% verified loss applied deck-wide (FEE-002)
780 |  |  |  | Technician estimate (P10, unverified)
1000 |  |  |  | Beyond technician estimate
1500 |  |  |  | ~38% of deck — substrate adequacy questionable (engineering judgment)
SWITCH 3 — Closure windows
If operations cannot confirm ≥6-hr night windows in writing (G7 contradicted), VE staging is infeasible as priced: each additional overnight window = $52,000 (A02 basis) and unapproved outages are non-payable service failures (FMR-010). More than ~60 extra windows would erode the VE advantage arithmetically, but the OPERATIONAL floor (1 ramp always active; memo §4) governs first — treat as a gate, not a cost.
SWITCH 4 — Evidence gates failing
Failure of G8 (FRP qualification), G1 (thickness < 0.31 in on verification), or unresolved G3/G4 (adhesion/chloride) each independently reverts the decision to the base scope regardless of cost, because VE function cannot be confirmed (23 U.S.C. 106(f)(2) function test, fhwa_ve_policy.pdf p.1).
NON-SWITCHES (checked, do not flip decision)
Quantity corrections (panels −2.4 SF; joints −4.4 LF) and 2%–4% discount rate move totals <1%; corrosion extent alone cannot flip the decision arithmetically within the deck area (breakeven ≈ 12,800 SF > 3,978.6 SF deck) — it matters through substrate adequacy (Switch 4), not price.

## Recommendation
Recommendation & Board Disposition
All figures reference Independent_Estimate / Lifecycle / Sensitivity_Switch cells so this sheet cannot drift from the model.
R1 — DEFENSIBLE BASE SCOPE (decision floor)
Full steel deck-panel replacement at SPECIFICATION-PAYABLE quantities: removal 3,977.6 SF (FMR-001); new orthotropic panels 3,980 SF (FMR-002);
skewed hinge/joint seals 1,255.6 LF geometric skew length (FMR-004); bearing-interface repairs 24 EA (FMR-005); coating + containment 5,240 SF DFT-passing only (FMR-007).
Independent base total (YOE $, incl. escalation + 4% DBB change-order contingency): =Independent_Estimate!F32 — see cell link below.
Base independent total ($):
VE independent total incl. corrosion risk allowance ($):
Independent first-cost advantage of VE ($):
Lifecycle PW advantage of VE, 40-yr @3% real ($):
R2 — VE DISPOSITION: CONDITIONAL APPROVAL (not acceptance as submitted)
The overlay/FRP VE concept is technically plausible and cost-advantaged on both first cost and 40-yr present worth at the CLAIMED 22-yr life.
It is NOT approvable as submitted because function-critical evidence is unverified or contradicted: FRP qualification (G8), steel thickness (G1), coating adhesion (G3, contradicted), chloride (G4), closure windows (G7, contradicted).
Per FHWA VE doctrine (23 U.S.C. 106(f)(2); fhwa_ve_policy.pdf p.1) VE must confirm needed functions and life-cycle cost — confirmation is impossible on the current evidence record.
DISPOSITION: approve the VE concept conditionally; fix acceptance criteria and complete gates G1–G8 actions (Evidence_Gates col G) BEFORE award; if any of G1/G3/G4/G7/G8 fails, revert to base scope R1.
Verified-life floor: if qualification verifies a system life below ~16 yr (Sensitivity_Switch Switch 1), revert to base — the PW advantage is exhausted by a second renewal.
R3 — ADD-ALTERNATES
A01 Expanded bearing NDE + contingent repair (12 EA, $175,200 submitted): ACCEPT NOW — bearing evidence is "conditional" (G6) and FMR-005 excludes unverified adjacent damage; NDE is the cheapest risk control available.
A02 Additional overnight closure windows (3 EA, $156,000 allowance): DEFER — do not buy closure windows until operations confirms the 6-hr window contradiction (G7) in writing.
R4 — UNRESOLVED BOUNDARIES (stated, not fabricated)
U1: takeoff totals 178.2 ft vs stated movable length 162.0 ft (~9.1% excess) — payable quantities assume full takeoff; confirm coverage before PS&E. Sensitivity: −9.1% panel scope if 162 ft governs.
U2: joint scope ambiguity — bid/takeoff joint network 1,255.3 LF vs two-hinge geometry 71.8 LF (N 30.8 ft @ 27°, S 31.2 ft @ 33°). Quantities carry the 48-segment network; if only two hinges are in scope, joint items reduce ~94%.
U3: corrosion extent — mapped 170 SF (payable) vs technician 780 SF vs 18% verified loss ≈ 716 SF deck-wide; VE carries a named risk allowance; base replacement is immune to this boundary.
U4: price basis — B02, B05, V02, V03 unit prices have no supplied independent benchmark (Market_Evidence); totals inherit submitted-price risk.
U5: escalation proxy is a ready-mix concrete PPI; no steel/fabrication index supplied.
U6: no agency discount rate supplied; 3% real assumed with 2–4% sensitivity (Lifecycle).
R5 — PROCESS NOTES
Quantities computed and independently checkable per BDM 12.2.2 (PDF p.6); final contract quantities require ±1% accuracy per BDM 12.2.4 (PDF p.7) — non-verified segments (32 of 48) must be field-checked to reach that tolerance.
Federal VE threshold (23 CFR 627.5: >$40M bridges) is not met at ~$6M; this VE review is a board-directed process following FHWA practice (fhwa_ve_policy.pdf pp.1–2).
Estimate file / BOE documentation duties per CEM §6.01/§6.04 (PDF pp.34–35) apply to any reissue of this estimate.