## 0_README
FAT INTEGRITY WORKBOOK — P-7402A (PWRI-220) RELEASE DECISION
Prepared by Rotating Equipment Reliability Lead ¦ 2026-08-25 ¦ Companion to rotating_equipment_release_board.pptx
PURPOSE
Determine whether pump P-7402A can be released for offshore commissioning after impeller work and the repeat FAT (2026-05-15).
This workbook is the auditable calculation basis. Every derived number (margins, pass/fail, counts, thresholds) is a live
formula. Input cells (blue) are literal transcriptions of the supplied source files; grey cells are computed.
DISPOSITION (computed on sheet 11_Disposition): CONDITIONAL RELEASE — release for offshore commissioning under a
restricted operating envelope, subject to closure actions C-01..C-12. NOT released for unrestricted service.
SOURCE FILES (read-only, /home/user/task/materials/)
fat_retest_measurements.csv ........... FAT overall vibration, original (2026-05-12) and retest (2026-05-15) runs
fat_spectral_events.csv ............... discrete-frequency events (1X, 2X, BPF, harmonics)
fat_runup_coastdown.csv ............... transient run-up / coast-down at PMP_DE_H
vibration_acceptance_rule_matrix.csv .. governing acceptance rules VR-000..VR-012
equipment_evidence_ledger.csv ......... evidence claims ME-001..ME-024 with verification states
sister_pump_field_baseline_P7402B.csv . sister-pump field baseline, trend and CMMS history
pump_specification_P7402A.xlsx ........ datasheet, Test Requirements sheet, performance curve
SHEET MAP
1_Rules .............. acceptance criteria input layer (current vs superseded limit retained side-by-side)
2_FAT_Raw ............ raw overall measurements (values only) + source-row locators
3_Overall_Eval ....... per-row margin and PASS/FAIL vs current limit (formulas)
4_Spectral_Eval ...... discrete-frequency check vs 2.5 mm/s peak (formulas) + attribution caveat
5_Transient .......... run-up/coast-down peak check (formulas)
6_Coverage_Check ..... required test matrix coverage; missing retest rows (formulas)
7_Sister_Baseline .... sister-pump field evidence (values + locators)
8_Sensitivity ........ rule-version dispute and measurement-uncertainty sensitivity (formulas)
9_Thresholds ......... derived commissioning alarm/trip scenarios (editable multipliers, formulas)
10_Exceptions ........ unresolved evidence register and closure actions C-01..C-12
11_Disposition ....... computed verdict and conditions (formulas)
STATED ASSUMPTIONS / UNRESOLVED BOUNDARIES (not fabricated — closure required)
A1. Acceptance limit: current extract VR-001 = 3.8 mm/s RMS (effective 2026-01-01). Superseded extract VR-000 = 4.2
retained for sensitivity only; withdrawal notice dated 2025-12-31 (vibration_acceptance_rule_matrix.csv row 2).
A2. Spectral file has no original/retest phase tag and uses different point naming (PNDE_/MDE_ vs PMP_NDE_/DRV_).
Discrete exceedances are therefore treated as evidence claims pending attribution (action C-06).
A3. No 4-hour mechanical-run duration record is supplied (VR-004); compliance unverified (action C-05).
A4. POR/AOR not stated on the datasheet (VR-008 = "case-specific"). Provisional envelope 80-105% BEP is assumed,
anchored to sister-pump duty (~95% BEP); engineering confirmation required (action C-07).
A5. Ledger claims marked contradicted (runout ME-007, baseplate ME-003) or field-verification-required
(alignment ME-004) are NOT accepted as facts (actions C-02..C-04).
A6. Alarm/trip values in 9_Thresholds are derived scenarios (editable), anchored to the sister-pump alarm event
(2.35 mm/s, 2026-05-22) — recommendations, not approved protection settings.
A7. Sister-pump file header says "Identical to P-2401A" — presumed typo for P-7402A; treated as claim, not fact.
A8. Retest covered pump points fully but driver points only at 100% and partially at 110%; original 2026-05-12
driver results passed at 60/80/90% BEP, so the gap is recorded as a deviation, not a failure (C-01).
COLOR LEGEND: blue = literal input from source ¦ grey = formula ¦ red = FAIL / open ¦ green = PASS / closed ¦ amber = caveat

## 1_Rules
ACCEPTANCE RULES — INPUT LAYER
Source: vibration_acceptance_rule_matrix.csv rows 2-14; pump_specification_P7402A.xlsx "Test Requirements" sheet
Rule ID | Domain | Requirement | Limit value | Unit | Scope text | Authority locator | Record status | Source row
VR-000 | overall housing vibration | RMS velocity | 4.2 | mm/s RMS | contract FAT equipment covered by cited clause | API 610 Table 8 / Test Requirements sheet | SUPERSEDED extract; withdrawal notice 2025-12-31 | rule matrix row 2
VR-001 | overall housing vibration | RMS velocity | 3.8 | mm/s RMS | contract FAT equipment covered by cited clause | API 610 Table 8 / Test Requirements sheet | CURRENT reference extract, effective 2026-01-01 | rule matrix row 3
VR-002 | discrete component | peak velocity | 2.5 | mm/s peak | each observed frequency component | API 610 Table 8 / Test Requirements sheet | reference extract | rule matrix row 4
VR-003 | FAT coverage | test matrix | 60¦90¦100¦110 | % BEP | all specified measurement locations | purchase specification FAT matrix | contract record | rule matrix row 5
VR-004 | mechanical run | elapsed time | 4 | hours minimum | stable operating run | API 610 mechanical run clause | reference extract — no duration record supplied | rule matrix row 6
VR-005 | bearing temperature | temperature | 82 | deg C (or ambient+45) | each bearing | Test Requirements sheet | reference extract | rule matrix row 7
VR-006 | shaft runout | TIR | 0.025 | mm | shaft acceptance | Test Requirements sheet | reference extract | rule matrix row 8
VR-007 | instrument calibration | certificate validity | current | status | all FAT channels | FAT quality plan | reference extract — cert valid-through 2026-05-31 | rule matrix row 9
VR-008 | POR/AOR | operating region | case-specific | % BEP | normal and transient duty | pump datasheet/performance curve | reference extract — AOR NOT stated on datasheet | rule matrix row 10
VR-009 | alarm | RMS trend threshold | derived | mm/s RMS | commissioning surveillance | supplied standards matrix | reference extract | rule matrix row 11
VR-010 | trip | RMS protection threshold | derived | mm/s RMS | machine protection | supplied standards matrix | reference extract | rule matrix row 12
VR-011 | missing retest | evidence closure | required | status | PMP_NDE_A at 60% BEP | FAT test matrix | reference extract — RETEST ROW MISSING | rule matrix row 13
VR-012 | field comparison | matched state | same condition | status | sister pump trend | P-7402B field file | reference extract | rule matrix row 14
KEY FORMULA REFERENCES
Current overall limit (mm/s RMS)
Superseded overall limit (mm/s RMS)
Discrete-frequency limit (mm/s peak)
Bearing temp limit (deg C)
Runout limit (mm TIR)

## 2_FAT_Raw
FAT OVERALL MEASUREMENTS — RAW INPUT
Source: fat_retest_measurements.csv rows 2-93 (verbatim values; blue cells = source transcription)
Measurement ID | Phase | Test date | Point | Direction | Flow %BEP | Overall RMS (mm/s) | Peak vel (mm/s) | Displ (µm) | Accel (g) | Temp (°C) | Source locator
VIB-0001 | original | 2026-05-12 | DRV_DE_H | Horizontal | 100 | 2.349 | 3.326 | 18.71 | 0.427 | 52.7 | fat_retest_measurements.csv row 2
VIB-0002 | original | 2026-05-12 | DRV_DE_V | Vertical | 100 | 1.913 | 2.711 | 15.24 | 0.358 | 52.5 | fat_retest_measurements.csv row 3
VIB-0003 | original | 2026-05-12 | DRV_DE_A | Axial | 100 | 4.013 | 5.68 | 32 | 0.731 | 53 | fat_retest_measurements.csv row 4
VIB-0004 | original | 2026-05-12 | DRV_NDE_H | Horizontal | 100 | 2.018 | 2.857 | 16.04 | 0.383 | 50.6 | fat_retest_measurements.csv row 5
VIB-0005 | original | 2026-05-12 | DRV_NDE_V | Vertical | 100 | 1.686 | 2.384 | 13.43 | 0.323 | 50.3 | fat_retest_measurements.csv row 6
VIB-0006 | original | 2026-05-12 | DRV_NDE_A | Axial | 100 | 1.864 | 2.638 | 14.87 | 0.356 | 50.8 | fat_retest_measurements.csv row 7
VIB-0007 | original | 2026-05-12 | PMP_DE_H | Horizontal | 100 | 3.001 | 4.244 | 23.9 | 0.548 | 56.9 | fat_retest_measurements.csv row 8
VIB-0008 | original | 2026-05-12 | PMP_DE_V | Vertical | 100 | 2.176 | 3.082 | 17.39 | 0.417 | 56.6 | fat_retest_measurements.csv row 9
VIB-0009 | original | 2026-05-12 | PMP_DE_A | Axial | 100 | 2.005 | 2.834 | 15.96 | 0.389 | 57.2 | fat_retest_measurements.csv row 10
VIB-0010 | original | 2026-05-12 | PMP_NDE_H | Horizontal | 100 | 2.49 | 3.529 | 19.86 | 0.473 | 55.3 | fat_retest_measurements.csv row 11
VIB-0011 | original | 2026-05-12 | PMP_NDE_V | Vertical | 100 | 2.049 | 2.898 | 16.35 | 0.393 | 55 | fat_retest_measurements.csv row 12
VIB-0012 | original | 2026-05-12 | PMP_NDE_A | Axial | 100 | 1.801 | 2.55 | 14.37 | 0.344 | 55.4 | fat_retest_measurements.csv row 13
VIB-0013 | original | 2026-05-12 | DRV_DE_H | Horizontal | 110 | 3.015 | 4.272 | 24.08 | 0.576 | 55.8 | fat_retest_measurements.csv row 14
VIB-0014 | original | 2026-05-12 | DRV_DE_V | Vertical | 110 | 2.464 | 3.485 | 19.69 | 0.474 | 55.5 | fat_retest_measurements.csv row 15
VIB-0015 | original | 2026-05-12 | DRV_DE_A | Axial | 110 | 3.204 | 4.536 | 25.53 | 0.62 | 56.1 | fat_retest_measurements.csv row 16
VIB-0016 | original | 2026-05-12 | DRV_NDE_H | Horizontal | 110 | 2.465 | 3.488 | 19.64 | 0.471 | 53.2 | fat_retest_measurements.csv row 17
VIB-0017 | original | 2026-05-12 | DRV_NDE_V | Vertical | 110 | 2.289 | 2.984 | 16.77 | 0.401 | 52.9 | fat_retest_measurements.csv row 18
VIB-0018 | original | 2026-05-12 | DRV_NDE_A | Axial | 110 | 2.194 | 3.105 | 17.49 | 0.424 | 53.4 | fat_retest_measurements.csv row 19
VIB-0019 | original | 2026-05-12 | PMP_DE_H | Horizontal | 110 | 5.413 | 7.651 | 43.2 | 1.031 | 61.3 | fat_retest_measurements.csv row 20
VIB-0020 | original | 2026-05-12 | PMP_DE_V | Vertical | 110 | 3.633 | 5.141 | 29 | 0.691 | 60.9 | fat_retest_measurements.csv row 21
VIB-0021 | original | 2026-05-12 | PMP_DE_A | Axial | 110 | 2.822 | 3.991 | 22.53 | 0.537 | 61.6 | fat_retest_measurements.csv row 22
VIB-0022 | original | 2026-05-12 | PMP_NDE_H | Horizontal | 110 | 3.875 | 5.482 | 30.92 | 0.742 | 58.7 | fat_retest_measurements.csv row 23
VIB-0023 | original | 2026-05-12 | PMP_NDE_V | Vertical | 110 | 2.997 | 4.245 | 23.94 | 0.573 | 58.4 | fat_retest_measurements.csv row 24
VIB-0024 | original | 2026-05-12 | PMP_NDE_A | Axial | 110 | 2.315 | 3.272 | 18.42 | 0.442 | 59 | fat_retest_measurements.csv row 25
VIB-0025 | original | 2026-05-12 | DRV_DE_H | Horizontal | 90_BEP | 1.904 | 2.691 | 15.21 | 0.362 | 51.6 | fat_retest_measurements.csv row 26
VIB-0026 | original | 2026-05-12 | DRV_DE_V | Vertical | 90_BEP | 1.582 | 2.238 | 12.6 | 0.302 | 51.3 | fat_retest_measurements.csv row 27
VIB-0027 | original | 2026-05-12 | DRV_DE_A | Axial | 90_BEP | 1.759 | 2.492 | 14.03 | 0.335 | 51.8 | fat_retest_measurements.csv row 28
VIB-0028 | original | 2026-05-12 | DRV_NDE_H | Horizontal | 90_BEP | 1.695 | 2.401 | 13.48 | 0.326 | 49.4 | fat_retest_measurements.csv row 29
VIB-0029 | original | 2026-05-12 | DRV_NDE_V | Vertical | 90_BEP | 1.403 | 1.983 | 11.19 | 0.264 | 49.1 | fat_retest_measurements.csv row 30
VIB-0030 | original | 2026-05-12 | DRV_NDE_A | Axial | 90_BEP | 1.483 | 2.097 | 11.87 | 0.286 | 49.6 | fat_retest_measurements.csv row 31
VIB-0031 | original | 2026-05-12 | PMP_DE_H | Horizontal | 90_BEP | 2.181 | 3.087 | 17.39 | 0.412 | 54.8 | fat_retest_measurements.csv row 32
VIB-0032 | original | 2026-05-12 | PMP_DE_V | Vertical | 90_BEP | 1.822 | 2.577 | 14.49 | 0.352 | 54.5 | fat_retest_measurements.csv row 33
VIB-0033 | original | 2026-05-12 | PMP_DE_A | Axial | 90_BEP | 1.593 | 2.259 | 12.7 | 0.302 | 55.1 | fat_retest_measurements.csv row 34
VIB-0034 | original | 2026-05-12 | PMP_NDE_H | Horizontal | 90_BEP | 1.979 | 2.795 | 15.81 | 0.377 | 53.2 | fat_retest_measurements.csv row 35
VIB-0035 | original | 2026-05-12 | PMP_NDE_V | Vertical | 90_BEP | 1.632 | 2.306 | 13.06 | 0.316 | 52.9 | fat_retest_measurements.csv row 36
VIB-0036 | original | 2026-05-12 | PMP_NDE_A | Axial | 90_BEP | 1.444 | 2.044 | 11.49 | 0.275 | 53.4 | fat_retest_measurements.csv row 37
VIB-0037 | original | 2026-05-12 | DRV_DE_H | Horizontal | 80 | 2.128 | 3.008 | 16.98 | 0.409 | 51 | fat_retest_measurements.csv row 38
VIB-0038 | original | 2026-05-12 | DRV_DE_V | Vertical | 80 | 1.76 | 2.49 | 13.99 | 0.34 | 50.7 | fat_retest_measurements.csv row 39
VIB-0039 | original | 2026-05-12 | DRV_DE_A | Axial | 80 | 2.318 | 3.281 | 18.53 | 0.445 | 51.3 | fat_retest_measurements.csv row 40
VIB-0040 | original | 2026-05-12 | DRV_NDE_H | Horizontal | 80 | 1.895 | 2.686 | 15.09 | 0.364 | 48.8 | fat_retest_measurements.csv row 41
VIB-0041 | original | 2026-05-12 | DRV_NDE_V | Vertical | 80 | 1.612 | 2.282 | 12.88 | 0.304 | 48.5 | fat_retest_measurements.csv row 42
VIB-0042 | original | 2026-05-12 | DRV_NDE_A | Axial | 80 | 1.716 | 2.432 | 13.69 | 0.326 | 49 | fat_retest_measurements.csv row 43
VIB-0043 | original | 2026-05-12 | PMP_DE_H | Horizontal | 80 | 2.604 | 3.682 | 20.75 | 0.498 | 55.6 | fat_retest_measurements.csv row 44
VIB-0044 | original | 2026-05-12 | PMP_DE_V | Vertical | 80 | 2.077 | 2.936 | 16.57 | 0.399 | 55.3 | fat_retest_measurements.csv row 45
VIB-0045 | original | 2026-05-12 | PMP_DE_A | Axial | 80 | 1.832 | 2.593 | 14.61 | 0.35 | 55.9 | fat_retest_measurements.csv row 46
VIB-0046 | original | 2026-05-12 | PMP_NDE_H | Horizontal | 80 | 2.391 | 3.384 | 19.04 | 0.455 | 53.8 | fat_retest_measurements.csv row 47
VIB-0047 | original | 2026-05-12 | PMP_NDE_V | Vertical | 80 | 1.967 | 2.779 | 15.72 | 0.375 | 53.5 | fat_retest_measurements.csv row 48
VIB-0048 | original | 2026-05-12 | PMP_NDE_A | Axial | 80 | 1.748 | 2.471 | 13.93 | 0.335 | 54 | fat_retest_measurements.csv row 49
VIB-0049 | original | 2026-05-12 | DRV_DE_H | Horizontal | 60 | 2.664 | 3.77 | 21.27 | 0.505 | 49.3 | fat_retest_measurements.csv row 50
VIB-0050 | original | 2026-05-12 | DRV_DE_V | Vertical | 60 | 2.146 | 3.041 | 17.09 | 0.407 | 49 | fat_retest_measurements.csv row 51
VIB-0051 | original | 2026-05-12 | DRV_DE_A | Axial | 60 | 2.936 | 4.153 | 23.43 | 0.563 | 49.6 | fat_retest_measurements.csv row 52
VIB-0052 | original | 2026-05-12 | DRV_NDE_H | Horizontal | 60 | 2.254 | 3.19 | 18.01 | 0.432 | 47.2 | fat_retest_measurements.csv row 53
VIB-0053 | original | 2026-05-12 | DRV_NDE_V | Vertical | 60 | 1.946 | 2.753 | 15.52 | 0.373 | 46.9 | fat_retest_measurements.csv row 54
VIB-0054 | original | 2026-05-12 | DRV_NDE_A | Axial | 60 | 2.124 | 3.008 | 16.97 | 0.406 | 47.4 | fat_retest_measurements.csv row 55
VIB-0055 | original | 2026-05-12 | PMP_DE_H | Horizontal | 60 | 3.895 | 5.507 | 31.1 | 0.743 | 54.1 | fat_retest_measurements.csv row 56
VIB-0056 | original | 2026-05-12 | PMP_DE_V | Vertical | 60 | 3.106 | 4.391 | 24.75 | 0.59 | 53.8 | fat_retest_measurements.csv row 57
VIB-0057 | original | 2026-05-12 | PMP_DE_A | Axial | 60 | 2.522 | 3.57 | 20.14 | 0.478 | 54.4 | fat_retest_measurements.csv row 58
VIB-0058 | original | 2026-05-12 | PMP_NDE_H | Horizontal | 60 | 4.91 | 6.946 | 39.18 | 0.931 | 52.3 | fat_retest_measurements.csv row 59
VIB-0059 | original | 2026-05-12 | PMP_NDE_V | Vertical | 60 | 5.659 | 8.006 | 45.17 | 1.08 | 52 | fat_retest_measurements.csv row 60
VIB-0060 | original | 2026-05-12 | PMP_NDE_A | Axial | 60 | 3.767 | 5.33 | 30.01 | 0.714 | 52.6 | fat_retest_measurements.csv row 61
VIB-0061 | retest | 2026-05-15 | PMP_DE_H | Horizontal | 100 | 2.623 | 3.716 | 20.92 | 0.5 | 56.3 | fat_retest_measurements.csv row 62
VIB-0062 | retest | 2026-05-15 | PMP_DE_V | Vertical | 100 | 2.042 | 2.89 | 16.23 | 0.387 | 56 | fat_retest_measurements.csv row 63
VIB-0063 | retest | 2026-05-15 | PMP_DE_A | Axial | 100 | 1.916 | 2.717 | 15.27 | 0.369 | 56.6 | fat_retest_measurements.csv row 64
VIB-0064 | retest | 2026-05-15 | PMP_NDE_H | Horizontal | 100 | 2.217 | 3.132 | 17.7 | 0.427 | 54.7 | fat_retest_measurements.csv row 65
VIB-0065 | retest | 2026-05-15 | PMP_NDE_V | Vertical | 100 | 1.831 | 2.588 | 14.63 | 0.348 | 54.4 | fat_retest_measurements.csv row 66
VIB-0066 | retest | 2026-05-15 | PMP_NDE_A | Axial | 100 | 1.626 | 2.305 | 12.97 | 0.309 | 54.9 | fat_retest_measurements.csv row 67
VIB-0067 | retest | 2026-05-15 | DRV_DE_H | Horizontal | 100 | 2.225 | 3.146 | 17.7 | 0.424 | 52.1 | fat_retest_measurements.csv row 68
VIB-0068 | retest | 2026-05-15 | DRV_DE_V | Vertical | 100 | 1.811 | 2.561 | 14.47 | 0.344 | 51.8 | fat_retest_measurements.csv row 69
VIB-0069 | retest | 2026-05-15 | DRV_DE_A | Axial | 100 | 2.806 | 3.968 | 22.41 | 0.534 | 52.4 | fat_retest_measurements.csv row 70
VIB-0070 | retest | 2026-05-15 | DRV_NDE_H | Horizontal | 100 | 1.916 | 2.717 | 15.27 | 0.369 | 50 | fat_retest_measurements.csv row 71
VIB-0071 | retest | 2026-05-15 | DRV_NDE_V | Vertical | 100 | 1.536 | 2.176 | 12.2 | 0.295 | 49.7 | fat_retest_measurements.csv row 72
VIB-0072 | retest | 2026-05-15 | DRV_NDE_A | Axial | 100 | 1.688 | 2.384 | 13.5 | 0.327 | 50.2 | fat_retest_measurements.csv row 73
VIB-0073 | retest | 2026-05-15 | PMP_DE_H | Horizontal | 110 | 3.89 | 5.505 | 30.97 | 0.741 | 59.9 | fat_retest_measurements.csv row 74
VIB-0074 | retest | 2026-05-15 | PMP_DE_V | Vertical | 110 | 2.743 | 3.881 | 21.84 | 0.517 | 59.6 | fat_retest_measurements.csv row 75
VIB-0075 | retest | 2026-05-15 | PMP_DE_A | Axial | 110 | 2.207 | 3.123 | 17.59 | 0.427 | 60.2 | fat_retest_measurements.csv row 76
VIB-0076 | retest | 2026-05-15 | PMP_NDE_H | Horizontal | 110 | 3.089 | 4.366 | 24.6 | 0.586 | 57.6 | fat_retest_measurements.csv row 77
VIB-0077 | retest | 2026-05-15 | PMP_NDE_V | Vertical | 110 | 2.432 | 3.443 | 19.38 | 0.463 | 57.3 | fat_retest_measurements.csv row 78
VIB-0078 | retest | 2026-05-15 | PMP_NDE_A | Axial | 110 | 1.953 | 2.766 | 15.56 | 0.376 | 57.8 | fat_retest_measurements.csv row 79
VIB-0079 | retest | 2026-05-15 | DRV_DE_H | Horizontal | 110 | 2.639 | 3.734 | 21.07 | 0.501 | 55.3 | fat_retest_measurements.csv row 80
VIB-0080 | retest | 2026-05-15 | DRV_DE_V | Vertical | 110 | 2.181 | 3.087 | 17.39 | 0.412 | 55 | fat_retest_measurements.csv row 81
VIB-0081 | retest | 2026-05-15 | DRV_DE_A | Axial | 110 | 2.95 | 4.171 | 23.49 | 0.559 | 55.6 | fat_retest_measurements.csv row 82
VIB-0082 | retest | 2026-05-15 | PMP_DE_H | Horizontal | 90_BEP | 1.999 | 2.832 | 15.93 | 0.385 | 54.3 | fat_retest_measurements.csv row 83
VIB-0083 | retest | 2026-05-15 | PMP_DE_V | Vertical | 90_BEP | 1.654 | 2.345 | 13.19 | 0.314 | 54 | fat_retest_measurements.csv row 84
VIB-0084 | retest | 2026-05-15 | PMP_DE_A | Axial | 90_BEP | 1.495 | 2.117 | 11.9 | 0.284 | 54.6 | fat_retest_measurements.csv row 85
VIB-0085 | retest | 2026-05-15 | PMP_NDE_H | Horizontal | 90_BEP | 1.739 | 2.461 | 13.83 | 0.336 | 52.7 | fat_retest_measurements.csv row 86
VIB-0086 | retest | 2026-05-15 | PMP_NDE_V | Vertical | 90_BEP | 1.453 | 2.056 | 11.56 | 0.276 | 52.4 | fat_retest_measurements.csv row 87
VIB-0087 | retest | 2026-05-15 | PMP_NDE_A | Axial | 90_BEP | 1.317 | 1.862 | 10.5 | 0.257 | 52.9 | fat_retest_measurements.csv row 88
VIB-0088 | retest | 2026-05-15 | PMP_DE_H | Horizontal | 60 | 3.395 | 4.802 | 27.12 | 0.652 | 53.4 | fat_retest_measurements.csv row 89
VIB-0089 | retest | 2026-05-15 | PMP_DE_V | Vertical | 60 | 2.717 | 3.841 | 21.65 | 0.52 | 53.1 | fat_retest_measurements.csv row 90
VIB-0090 | retest | 2026-05-15 | PMP_DE_A | Axial | 60 | 2.282 | 3.225 | 18.22 | 0.44 | 53.7 | fat_retest_measurements.csv row 91
VIB-0091 | retest | 2026-05-15 | PMP_NDE_H | Horizontal | 60 | 4.159 | 5.886 | 33.17 | 0.79 | 51.6 | fat_retest_measurements.csv row 92
VIB-0092 | retest | 2026-05-15 | PMP_NDE_V | Vertical | 60 | 4.495 | 6.356 | 35.8 | 0.854 | 51.3 | fat_retest_measurements.csv row 93

## 3_Overall_Eval
OVERALL VIBRATION EVALUATION vs CURRENT LIMIT (VR-001 = 3.8 mm/s RMS)
All margins/verdicts are formulas referencing 2_FAT_Raw and 1_Rules. Verdict colours via conditional formatting.
Measurement ID | Phase | Point / Dir | Flow %BEP | Overall RMS | Limit | Margin (mm/s) | Margin % | Verdict | Envelope-flag value (retest 90/100)
SUMMARY (formulas)
Retest points evaluated
Retest PASS
Retest FAIL
Original FAIL
Retest worst value (mm/s)
Best retest margin below limit (mm/s)

## 4_Spectral_Eval
DISCRETE-FREQUENCY CHECK vs VR-002 (2.5 mm/s peak)
CAVEAT A2: source file carries no original/retest phase tag and point naming differs from FAT sheet — verdicts are provisional claims.
Event ID | Point | Flow | Freq (Hz) | Amplitude (mm/s) | Order | Limit | Margin | Provisional verdict | Technician annotation | Source row
SP-001 | PMP_DE_H | 100 | 49.663 | 1.997 | 1X |  |  |  | Shaft rotational speed - observed | fat_spectral_events.csv row 2
SP-002 | PMP_DE_H | 100 | 99.337 | 0.874 | 2X |  |  |  | Misalignment indicator - observed | fat_spectral_events.csv row 3
SP-003 | PMP_DE_H | 100 | 148.99 | 0.218 | 3X |  |  |  | observed harmonic | fat_spectral_events.csv row 4
SP-004 | PMP_DE_H | 100 | 298 | 0.707 | BPF (6X) |  |  |  | Blade pass frequency - observed | fat_spectral_events.csv row 5
SP-005 | PMP_DE_H | 100 | 347.663 | 0.125 | BPF+1X |  |  |  | BPF sideband | fat_spectral_events.csv row 6
SP-006 | PMP_DE_H | 100 | 248.337 | 0.094 | BPF-1X |  |  |  | BPF sideband | fat_spectral_events.csv row 7
SP-007 | PMP_DE_H | 100 | 596 | 0.156 | 2xBPF |  |  |  | Second harmonic of BPF | fat_spectral_events.csv row 8
SP-008 | PMP_DE_H | 110 | 49.663 | 2.85 | 1X |  |  |  | observed - high flow hydraulic loads | fat_spectral_events.csv row 9
SP-009 | PMP_DE_H | 110 | 99.337 | 1.695 | 2X |  |  |  | observed 2X suggests increased radial load | fat_spectral_events.csv row 10
SP-010 | PMP_DE_H | 110 | 148.99 | 0.499 | 3X |  |  |  | observed harmonic | fat_spectral_events.csv row 11
SP-011 | PMP_DE_H | 110 | 298 | 2.964 | BPF (6X) |  |  |  | observed - high flow cavitation/turbulence at volute | fat_spectral_events.csv row 12
SP-012 | PMP_DE_H | 110 | 347.663 | 0.749 | BPF+1X |  |  |  | observed sideband - modulated BPF | fat_spectral_events.csv row 13
SP-013 | PMP_DE_H | 110 | 248.337 | 0.676 | BPF-1X |  |  |  | observed sideband - modulated BPF | fat_spectral_events.csv row 14
SP-014 | PMP_DE_H | 110 | 596 | 0.946 | 2xBPF |  |  |  | observed second harmonic of BPF | fat_spectral_events.csv row 15
SP-015 | PMP_DE_H | 110 | 198.663 | 0.291 | 4X |  |  |  | observed harmonic | fat_spectral_events.csv row 16
SP-016 | PMP_DE_H | 90_BEP | 49.663 | 1.508 | 1X |  |  |  | Lowest 1X at BEP - balanced hydraulic load | fat_spectral_events.csv row 17
SP-017 | PMP_DE_H | 90_BEP | 99.337 | 0.541 | 2X |  |  |  | Low 2X - good alignment indication | fat_spectral_events.csv row 18
SP-018 | PMP_DE_H | 90_BEP | 298 | 0.426 | BPF (6X) |  |  |  | Minimum BPF at BEP - optimal impeller/volute interaction | fat_spectral_events.csv row 19
SP-019 | PMP_DE_H | 90_BEP | 347.663 | 0.062 | BPF+1X |  |  |  | Minimal sideband | fat_spectral_events.csv row 20
SP-020 | PMP_DE_H | 90_BEP | 248.337 | 0.052 | BPF-1X |  |  |  | Minimal sideband | fat_spectral_events.csv row 21
SP-021 | PMP_DE_H | 90_BEP | 596 | 0.083 | 2xBPF |  |  |  | observed | fat_spectral_events.csv row 22
SP-022 | PMP_DE_H | 60 | 49.663 | 2.579 | 1X |  |  |  | observed - hydraulic instability at low flow | fat_spectral_events.csv row 23
SP-023 | PMP_DE_H | 60 | 99.337 | 1.258 | 2X |  |  |  | observed - possible shaft deflection from radial thrust | fat_spectral_events.csv row 24
SP-024 | PMP_DE_H | 60 | 298 | 1.591 | BPF (6X) |  |  |  | observed BPF - recirculation effects | fat_spectral_events.csv row 25
SP-025 | PMP_DE_H | 60 | 347.663 | 0.395 | BPF+1X |  |  |  | Modulated sideband | fat_spectral_events.csv row 26
SP-026 | PMP_DE_H | 60 | 248.337 | 0.354 | BPF-1X |  |  |  | Modulated sideband | fat_spectral_events.csv row 27
SP-027 | PMP_DE_H | 60 | 596 | 0.426 | 2xBPF |  |  |  | observed | fat_spectral_events.csv row 28
SP-028 | PNDE_H | 100 | 49.663 | 1.747 | 1X |  |  |  | observed shaft speed component | fat_spectral_events.csv row 29
SP-029 | PNDE_H | 100 | 99.337 | 0.738 | 2X |  |  |  | observed | fat_spectral_events.csv row 30
SP-030 | PNDE_H | 100 | 298 | 0.541 | BPF (6X) |  |  |  | observed | fat_spectral_events.csv row 31
SP-031 | PNDE_H | 100 | 596 | 0.114 | 2xBPF |  |  |  | observed | fat_spectral_events.csv row 32
SP-032 | PNDE_H | 110 | 49.663 | 2.236 | 1X |  |  |  | observed | fat_spectral_events.csv row 33
SP-033 | PNDE_H | 110 | 99.337 | 1.331 | 2X |  |  |  | observed - increased bearing load at high flow | fat_spectral_events.csv row 34
SP-034 | PNDE_H | 110 | 298 | 1.997 | BPF (6X) |  |  |  | observed - hydraulic excitation transmitted to NDE bearing | fat_spectral_events.csv row 35
SP-035 | PNDE_H | 110 | 347.663 | 0.541 | BPF+1X |  |  |  | Sideband activity | fat_spectral_events.csv row 36
SP-036 | PNDE_H | 110 | 248.337 | 0.489 | BPF-1X |  |  |  | Sideband activity | fat_spectral_events.csv row 37
SP-037 | PNDE_H | 110 | 596 | 0.395 | 2xBPF |  |  |  | observed | fat_spectral_events.csv row 38
SP-038 | PNDE_H | 90_BEP | 49.663 | 1.362 | 1X |  |  |  | Minimum at BEP | fat_spectral_events.csv row 39
SP-039 | PNDE_H | 90_BEP | 99.337 | 0.447 | 2X |  |  |  | Low | fat_spectral_events.csv row 40
SP-040 | PNDE_H | 90_BEP | 298 | 0.333 | BPF (6X) |  |  |  | Minimum at BEP | fat_spectral_events.csv row 41
SP-041 | PNDE_H | 90_BEP | 596 | 0.062 | 2xBPF |  |  |  | observed | fat_spectral_events.csv row 42
SP-042 | PNDE_H | 60 | 49.663 | 2.964 | 1X |  |  |  | High - significant radial thrust at low flow | fat_spectral_events.csv row 43
SP-043 | PNDE_H | 60 | 99.337 | 1.529 | 2X |  |  |  | High - shaft deflection response | fat_spectral_events.csv row 44
SP-044 | PNDE_H | 60 | 298 | 1.227 | BPF (6X) |  |  |  | observed | fat_spectral_events.csv row 45
SP-045 | PNDE_H | 60 | 596 | 0.302 | 2xBPF |  |  |  | observed | fat_spectral_events.csv row 46
SP-046 | PNDE_H | 60 | 347.663 | 0.322 | BPF+1X |  |  |  | Modulated | fat_spectral_events.csv row 47
SP-047 | MDE_H | 100 | 49.663 | 1.643 | 1X |  |  |  | observed | fat_spectral_events.csv row 48
SP-048 | MDE_H | 100 | 99.337 | 0.645 | 2X |  |  |  | observed coupling/alignment | fat_spectral_events.csv row 49
SP-049 | MDE_H | 100 | 298 | 0.25 | BPF (6X) |  |  |  | Transmitted from pump - low | fat_spectral_events.csv row 50
SP-050 | MDE_H | 110 | 49.663 | 2.028 | 1X |  |  |  | observed from increased torque load | fat_spectral_events.csv row 51
SP-051 | MDE_H | 110 | 99.337 | 0.946 | 2X |  |  |  | Coupling response to increased load | fat_spectral_events.csv row 52
SP-052 | MDE_H | 110 | 298 | 0.489 | BPF (6X) |  |  |  | Transmitted hydraulic excitation | fat_spectral_events.csv row 53
SP-053 | MDE_H | 90_BEP | 49.663 | 1.331 | 1X |  |  |  | Minimum at BEP | fat_spectral_events.csv row 54
SP-054 | MDE_H | 90_BEP | 99.337 | 0.426 | 2X |  |  |  | Good | fat_spectral_events.csv row 55
SP-055 | MDE_H | 90_BEP | 298 | 0.156 | BPF (6X) |  |  |  | Minimal transmission | fat_spectral_events.csv row 56
SP-056 | MDE_H | 60 | 49.663 | 1.789 | 1X |  |  |  | Moderate increase at low flow | fat_spectral_events.csv row 57
SP-057 | MDE_H | 60 | 99.337 | 0.884 | 2X |  |  |  | observed - coupling responding to radial thrust | fat_spectral_events.csv row 58
SP-058 | MDE_H | 60 | 298 | 0.395 | BPF (6X) |  |  |  | Transmitted from pump | fat_spectral_events.csv row 59
SP-059 | MDE_A | 100 | 49.663 | 2.756 | 1X |  |  |  | observed axial 1X - monitor for thrust bearing wear | fat_spectral_events.csv row 60
SP-060 | MDE_A | 100 | 99.337 | 1.165 | 2X |  |  |  | observed axial 2X - possible angular misalignment | fat_spectral_events.csv row 61
SP-061 | MDE_A | 100 | 298 | 0.364 | BPF (6X) |  |  |  | observed axial BPF | fat_spectral_events.csv row 62
SP-062 | MDE_A | 100 | 148.99 | 0.291 | 3X |  |  |  | observed harmonic | fat_spectral_events.csv row 63
Discrete exceedance count (provisional)
Exceedances are concentrated at 60% and 110% BEP + one axial driver event at 100% (SP-059); attribution to run phase unresolved (C-06).

## 5_Transient
TRANSIENT RUN-UP / COAST-DOWN — PMP_DE_H
Source: fat_runup_coastdown.csv rows 2-50. Peak and resonance-window checks are formulas.
Phase | Speed (rpm) | Overall RMS (mm/s) | Point | Direction | Elapsed (s) | Operator note | Source row | Resonance-window flag | Rated-speed flag
run-up | 0 | 0.021 | PMP_DE_H | Horizontal | 0 | Baseline noise floor | fat_runup_coastdown.csv row 2
run-up | 151 | 0.083 | PMP_DE_H | Horizontal | 2 | Initial rotation | fat_runup_coastdown.csv row 3
run-up | 302 | 0.156 | PMP_DE_H | Horizontal | 4 | Low speed | fat_runup_coastdown.csv row 4
run-up | 453 | 0.25 | PMP_DE_H | Horizontal | 6 | Increasing | fat_runup_coastdown.csv row 5
run-up | 604.1 | 0.395 | PMP_DE_H | Horizontal | 8 | Oil film establishing | fat_runup_coastdown.csv row 6
run-up | 755.1 | 0.541 | PMP_DE_H | Horizontal | 10 |  | fat_runup_coastdown.csv row 7
run-up | 906.1 | 0.738 | PMP_DE_H | Horizontal | 12 |  | fat_runup_coastdown.csv row 8
run-up | 1057.1 | 0.926 | PMP_DE_H | Horizontal | 14 |  | fat_runup_coastdown.csv row 9
run-up | 1208.1 | 1.186 | PMP_DE_H | Horizontal | 16 | Approaching fluid coupling engagement | fat_runup_coastdown.csv row 10
run-up | 1359.1 | 1.435 | PMP_DE_H | Horizontal | 18 |  | fat_runup_coastdown.csv row 11
run-up | 1510.1 | 1.789 | PMP_DE_H | Horizontal | 20 | Mid-speed | fat_runup_coastdown.csv row 12
run-up | 1661.1 | 2.09 | PMP_DE_H | Horizontal | 22 |  | fat_runup_coastdown.csv row 13
run-up | 1812.2 | 2.444 | PMP_DE_H | Horizontal | 24 | Structural resonance proximity | fat_runup_coastdown.csv row 14
run-up | 1963.2 | 2.787 | PMP_DE_H | Horizontal | 26 | local response feature | fat_runup_coastdown.csv row 15
run-up | 2114.2 | 2.517 | PMP_DE_H | Horizontal | 28 | Past resonance - declining | fat_runup_coastdown.csv row 16
run-up | 2265.2 | 2.267 | PMP_DE_H | Horizontal | 30 |  | fat_runup_coastdown.csv row 17
run-up | 2416.2 | 2.402 | PMP_DE_H | Horizontal | 32 | Minor secondary response | fat_runup_coastdown.csv row 18
run-up | 2567.2 | 2.621 | PMP_DE_H | Horizontal | 34 |  | fat_runup_coastdown.csv row 19
run-up | 2718.2 | 2.818 | PMP_DE_H | Horizontal | 36 | Approaching rated speed | fat_runup_coastdown.csv row 20
run-up | 2818.9 | 2.933 | PMP_DE_H | Horizontal | 38 |  | fat_runup_coastdown.csv row 21
run-up | 2899.5 | 2.891 | PMP_DE_H | Horizontal | 40 | Near rated | fat_runup_coastdown.csv row 22
run-up | 2939.7 | 2.922 | PMP_DE_H | Horizontal | 42 |  | fat_runup_coastdown.csv row 23
run-up | 2969.9 | 2.954 | PMP_DE_H | Horizontal | 43.5 |  | fat_runup_coastdown.csv row 24
run-up | 2980 | 2.964 | PMP_DE_H | Horizontal | 45 | Rated speed - steady state | fat_runup_coastdown.csv row 25
run-up | 2980 | 2.964 | PMP_DE_H | Horizontal | 60 | Steady state confirmed at 15s dwell | fat_runup_coastdown.csv row 26
run-up | 2980 | 2.954 | PMP_DE_H | Horizontal | 90 | Thermal stabilization | fat_runup_coastdown.csv row 27
run-up | 2980 | 2.964 | PMP_DE_H | Horizontal | 120 | Fully stabilized | fat_runup_coastdown.csv row 28
coast-down | 2980 | 2.964 | PMP_DE_H | Horizontal | 0 | Trip initiated | fat_runup_coastdown.csv row 29
coast-down | 2919.6 | 2.902 | PMP_DE_H | Horizontal | 1.5 | Decelerating | fat_runup_coastdown.csv row 30
coast-down | 2818.9 | 2.787 | PMP_DE_H | Horizontal | 3.5 |  | fat_runup_coastdown.csv row 31
coast-down | 2718.2 | 2.652 | PMP_DE_H | Horizontal | 5.5 |  | fat_runup_coastdown.csv row 32
coast-down | 2567.2 | 2.506 | PMP_DE_H | Horizontal | 8 |  | fat_runup_coastdown.csv row 33
coast-down | 2416.2 | 2.371 | PMP_DE_H | Horizontal | 10.5 |  | fat_runup_coastdown.csv row 34
coast-down | 2265.2 | 2.236 | PMP_DE_H | Horizontal | 13 |  | fat_runup_coastdown.csv row 35
coast-down | 2114.2 | 2.475 | PMP_DE_H | Horizontal | 15.5 | local response feature | fat_runup_coastdown.csv row 36
coast-down | 1963.2 | 2.829 | PMP_DE_H | Horizontal | 18 | local response feature on coast-down | fat_runup_coastdown.csv row 37
coast-down | 1812.2 | 2.402 | PMP_DE_H | Horizontal | 20.5 | Past resonance | fat_runup_coastdown.csv row 38
coast-down | 1661.1 | 1.924 | PMP_DE_H | Horizontal | 23 |  | fat_runup_coastdown.csv row 39
coast-down | 1510.1 | 1.581 | PMP_DE_H | Horizontal | 25.5 |  | fat_runup_coastdown.csv row 40
coast-down | 1359.1 | 1.258 | PMP_DE_H | Horizontal | 28 |  | fat_runup_coastdown.csv row 41
coast-down | 1208.1 | 0.978 | PMP_DE_H | Horizontal | 30.5 |  | fat_runup_coastdown.csv row 42
coast-down | 1057.1 | 0.749 | PMP_DE_H | Horizontal | 33 |  | fat_runup_coastdown.csv row 43
coast-down | 906.1 | 0.562 | PMP_DE_H | Horizontal | 35.5 |  | fat_runup_coastdown.csv row 44
coast-down | 755.1 | 0.406 | PMP_DE_H | Horizontal | 38 |  | fat_runup_coastdown.csv row 45
coast-down | 604.1 | 0.281 | PMP_DE_H | Horizontal | 40.5 |  | fat_runup_coastdown.csv row 46
coast-down | 453 | 0.187 | PMP_DE_H | Horizontal | 43 |  | fat_runup_coastdown.csv row 47
coast-down | 302 | 0.114 | PMP_DE_H | Horizontal | 45.5 |  | fat_runup_coastdown.csv row 48
coast-down | 151 | 0.062 | PMP_DE_H | Horizontal | 48 |  | fat_runup_coastdown.csv row 49
coast-down | 0 | 0.021 | PMP_DE_H | Horizontal | 52 | Full stop - coast-down time 52 seconds | fat_runup_coastdown.csv row 50
Transient peak overall (mm/s)
Speed at peak (rpm)
Resonance-window peak 1800-2150 rpm (mm/s)
Verdict vs current limit
Steady-state at rated 2980 rpm (mm/s)
Only PMP_DE_H was recorded during the transient — other bearings not covered (unresolved boundary).

## 6_Coverage_Check
REQUIRED TEST-MATRIX COVERAGE (VR-003: 60 ¦ 90 ¦ 100 ¦ 110 % BEP, all locations)
COUNTIFS formulas against 2_FAT_Raw. Any retest count of 0 = evidence gap.
Point | Direction | Flow %BEP | Original rows | Retest rows | Coverage status | Note
DRV_DE_H | Horizontal | 60 |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_DE_H | Horizontal | 90_BEP |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_DE_H | Horizontal | 100
DRV_DE_H | Horizontal | 110
DRV_DE_V | Vertical | 60 |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_DE_V | Vertical | 90_BEP |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_DE_V | Vertical | 100
DRV_DE_V | Vertical | 110
DRV_DE_A | Axial | 60 |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_DE_A | Axial | 90_BEP |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_DE_A | Axial | 100
DRV_DE_A | Axial | 110
DRV_NDE_H | Horizontal | 60 |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_NDE_H | Horizontal | 90_BEP |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_NDE_H | Horizontal | 100
DRV_NDE_H | Horizontal | 110 |  |  |  | driver NDE not retested at 110%; original passed — deviation, see C-01
DRV_NDE_V | Vertical | 60 |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_NDE_V | Vertical | 90_BEP |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_NDE_V | Vertical | 100
DRV_NDE_V | Vertical | 110 |  |  |  | driver NDE not retested at 110%; original passed — deviation, see C-01
DRV_NDE_A | Axial | 60 |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_NDE_A | Axial | 90_BEP |  |  |  | driver point not retested; original result passed — deviation, see C-01
DRV_NDE_A | Axial | 100
DRV_NDE_A | Axial | 110 |  |  |  | driver NDE not retested at 110%; original passed — deviation, see C-01
PMP_DE_H | Horizontal | 60
PMP_DE_H | Horizontal | 90_BEP
PMP_DE_H | Horizontal | 100
PMP_DE_H | Horizontal | 110
PMP_DE_V | Vertical | 60
PMP_DE_V | Vertical | 90_BEP
PMP_DE_V | Vertical | 100
PMP_DE_V | Vertical | 110
PMP_DE_A | Axial | 60
PMP_DE_A | Axial | 90_BEP
PMP_DE_A | Axial | 100
PMP_DE_A | Axial | 110
PMP_NDE_H | Horizontal | 60
PMP_NDE_H | Horizontal | 90_BEP
PMP_NDE_H | Horizontal | 100
PMP_NDE_H | Horizontal | 110
PMP_NDE_V | Vertical | 60
PMP_NDE_V | Vertical | 90_BEP
PMP_NDE_V | Vertical | 100
PMP_NDE_V | Vertical | 110
PMP_NDE_A | Axial | 60 |  |  |  | VR-011 flagged gap (rule matrix row 13); retest row absent (file ends VIB-0092)
PMP_NDE_A | Axial | 90_BEP
PMP_NDE_A | Axial | 100
PMP_NDE_A | Axial | 110
Retest rows missing vs required matrix
Of which inside retest pump scope (PMP points)
Hard evidence gap per VR-011: PMP_NDE_A @ 60% BEP (the only PMP-point miss). Driver misses are deviations because the original run passed at those points.

## 7_Sister_Baseline
SISTER PUMP P-7402B FIELD EVIDENCE
Source: sister_pump_field_baseline_P7402B.csv (values verbatim; section/row locators retained)
File context | Equipment PWRI-220, Tag P-7402B, commissioned 2025-06-20; survey 2026-12-10, 12,840 h; ~95% BEP estimated (file rows 1-5, 8-9)
Header states "Identical to P-2401A" — presumed typo for P-7402A (assumption A7)
OVERALL READINGS AT ~95% BEP (file Section 1, rows 12-24)
Point | Direction | Overall RMS (mm/s) | Note | Source row
MDE_H | Horizontal | 1.42 | Normal | sister file row 13
MDE_A | Axial | 1.55 | Slightly elevated axial - monitor | sister file row 15
PDE_H | Horizontal | 1.72 | Normal | sister file row 19
PNDE_H | Horizontal | 1.51 | Normal | sister file row 22
PNDE_A | Axial | 1.08 | Normal | sister file row 24
TREND — PDE_H overall (file Section 4, rows 40-49)
Survey date | RMS (mm/s) | Hours | Note | Source row
2025-07-15 | 1.45 | 580 | Post-commissioning baseline | sister file row 41
2025-10-12 | 1.48 | 2720 | Stable | sister file row 42
2026-01-18 | 1.52 | 4980 | Stable | sister file row 43
2026-04-11 | 1.68 | 6940 | Slight increase - continued monitoring | sister file row 44
2026-05-22 | 2.35 | 7920 | ALARM - bearing noise audible | sister file row 45
2026-06-05 | 1.38 | 8040 | Post-repair baseline - restored | sister file row 47
2026-09-19 | 1.55 | 10560 | Normal | sister file row 48
2026-12-10 | 1.72 | 12840 | Normal - slight upward trend | sister file row 49
KEY MAINTENANCE EVENTS (file Section 5, rows 52-57)
WO | Date | Type | Description / root cause | Source row
WO-2026-0847 | 2026-05-28 | Corrective | DE bearing 6316 C3 replacement - inner race spalling; root cause: contaminated lubricant, WATER INGRESS via breather | sister file row 56
WO-2026-1103 | 2026-09-20 | Preventive | Oil change + desiccant breather upgrade to prevent recurrence | sister file row 57
Reference: current field baseline PDE_H (mm/s)
Reference: observed sister ALARM level (mm/s)
Same DE bearing type as P-7402A (6316 C3, datasheet row "Bearing Type - DE") — water-ingress lesson directly transferable (C-09).

## 8_Sensitivity
SENSITIVITY & UNCERTAINTY
How robust is the decision to the rule-version dispute (A1) and to measurement uncertainty? All counts are formulas.
S1. RULE-VERSION DISPUTE — retest FAIL count under each limit
Scenario | Limit (mm/s) | Retest FAILs | Worst fail margin | Reading
Current extract VR-001 (effective 2026-01-01)
Superseded extract VR-000 (withdrawn 2025-12-31)
S2. MEASUREMENT-UNCERTAINTY SENSITIVITY — uncertainty needed to flip each retest exceedance
Retest exceedance | Value (mm/s) | Limit | Over-limit % | Uncertainty to flip verdict
PMP_NDE_V @ 60% BEP (VIB-0092, fat_retest row 92) | 4.495
PMP_NDE_H @ 60% BEP (VIB-0091, fat_retest row 91) | 4.159
PMP_DE_H @ 110% BEP (VIB-0073, fat_retest row 73) | 3.89
PMP_DE_H @ 110% flips on ≥2.4% uncertainty (marginal); the two 60% BEP NDE exceedances (≥9.4%) are robust to plausible Class-1 instrument uncertainty.
S3. WHERE THE ENVELOPE HOLDS
Retest max at 90-100% BEP (mm/s)
Margin below limit at 90-100% BEP (mm/s)
RESULT: inside the provisional 80-105% BEP envelope every measured point passes with ≥26% margin. Envelope assumption A4 must be confirmed (C-07).

## 9_Thresholds
DERIVED COMMISSIONING ALARM / TRIP SCENARIOS (VR-009 / VR-010)
Blue multiplier cells are editable scenario inputs — NOT approved protection settings. Anchors: sister baseline & alarm event (7_Sister_Baseline).
Parameter | Value | Unit | Basis / locator
Sister field baseline PDE_H @ ~95% BEP |  | mm/s RMS | 7_Sister_Baseline (sister file row 49)
Sister observed ALARM level 2026-05-22 |  | mm/s RMS | sister file row 45; preceded WO-2026-0847 bearing failure
FAT acceptance ceiling (current) |  | mm/s RMS | VR-001 / Test Requirements sheet
Alarm multiplier (editable) | 1.4 | x baseline | scenario input; 1.4 x 1.72 = 2.41, consistent with observed 2.35 alarm event
Trip margin below ceiling (editable) | 0.3 | mm/s RMS | scenario input; keeps trip below 3.8 acceptance ceiling
DERIVED VALUES (formulas)
Recommended commissioning ALARM |  | mm/s RMS | baseline x multiplier
Recommended commissioning TRIP |  | mm/s RMS | ceiling minus margin
Consistency check: alarm <= observed sister alarm?
Consistency check: trip < FAT exceedance floor?
Action C-08: settings to be approved by machinery protection authority before start-up; values above are recommendations.

## 10_Exceptions
EXCEPTIONS / UNRESOLVED EVIDENCE REGISTER
Ledger evidence states from equipment_evidence_ledger.csv; nothing below is accepted as fact until closed.
ID | Item | Evidence claim | Evidence state | Impact on release | Closure action | Source locator
E-01 | Shaft runout record | 0.021 mm TIR | CONTRADICTED | Numeric claim passes 0.025 limit but evidence is contradicted — cannot be relied on | C-02: re-measure runout pre-commissioning | ledger ME-007; rule VR-006
E-02 | Cold alignment report | 0.045 mm offset | FIELD-VERIFICATION-REQUIRED | Alignment unverified at site; 2X spectral activity claims misalignment contribution | C-03: field laser alignment verification | ledger ME-004; SP-002/SP-009
E-03 | Baseplate level survey | 0.08 mm/m | CONTRADICTED | Foundation quality unresolved — affects installed vibration | C-04: resolve survey contradiction | ledger ME-003
E-04 | Mechanical-run duration | 4 h minimum | NO RECORD SUPPLIED | VR-004 compliance unverified | C-05: obtain signed run-duration record | rule VR-004
E-05 | Missing retest point | PMP_NDE_A @ 60% BEP | REQUIRED / ABSENT | Matrix incomplete at the failing flow point | C-01: close retest point or formal deviation | rule VR-011; fat_retest file ends VIB-0092
E-06 | Spectral phase attribution | 5 discrete exceedances | AMBIGUOUS | Discrete verdicts provisional until tied to run phase | C-06: attribute SP-008/011/022/042/059 | fat_spectral_events.csv (no phase column)
E-07 | POR / AOR | case-specific | NOT STATED ON DATASHEET | Envelope restriction is an assumption | C-07: engineering to confirm POR/AOR | rule VR-008; datasheet
E-08 | Instrument calibration | valid-through 2026-05-31 | INDEPENDENTLY-VERIFIED | Cert covered FAT date 2026-05-15 — CLOSED for FAT; recertify before offshore use | C-12: verify calibration currency offshore | ledger ME-002/ME-010
E-09 | Contract limit version | 3.8 vs 4.2 mm/s | VERSION DISPUTE | Superseded 4.2 would not rescue worst fail (8_Sensitivity) | Resolved: apply current 3.8 | rule VR-000 vs VR-001
E-10 | Sister file header typo | "Identical to P-2401A" | CLAIM | Treat sister data as analogous, pending confirmation of identity | C-07 (bundle): confirm comparability | sister file row 1

## 11_Disposition
DISPOSITION — COMPUTED VERDICT
Verdict cell is a formula over the evaluation sheets. Conditions C-01..C-12 below.
Retest points evaluated
Retest exceedances vs 3.8 mm/s
Hard evidence gap (VR-011 missing PMP_NDE_A @60%)
Max inside 90-100% BEP band (mm/s)
VERDICT
CONDITIONS / CLOSURE ACTIONS (owners are recommended roles, not assigned authority)
ID | Gate | Action
C-01 | Evidence | Close missing retest point PMP_NDE_A @ 60% BEP (VR-011) or record a formal, risk-assessed deviation covering it and the un-retested driver points.
C-02 | Evidence | Re-measure shaft runout vs 0.025 mm TIR (VR-006); ledger claim ME-007 is contradicted.
C-03 | Evidence | Field laser-alignment verification at installation (claim ME-004, 0.045 mm, field-verification-required).
C-04 | Evidence | Resolve baseplate level survey contradiction (ME-003, 0.08 mm/m).
C-05 | Evidence | Obtain signed 4-hour mechanical-run duration record (VR-004); none supplied.
C-06 | Evidence | Attribute spectral exceedances SP-008/011/022/042/059 to run phase; re-evaluate VR-002.
C-07 | Operating | Engineering to confirm POR/AOR (VR-008); until then restrict to provisional 80-105% BEP envelope.
C-08 | Protection | Approve & implement commissioning alarm/trip per 9_Thresholds (recommendation ~2.4 / ~3.5 mm/s RMS).
C-09 | Reliability | Fit desiccant breather + oil-analysis program (sister WO-2026-0847/1103 water-ingress lesson; same 6316 C3 DE bearing).
C-10 | Transient | Minimise dwell in 1800-2150 rpm resonance window during run-up/coast-down (5_Transient); log every transient.
C-11 | Commissioning | Monitored commissioning run at 90-100% BEP with hold points; no sustained operation <80% or >105% BEP pending C-07.
C-12 | Quality | Verify instrument calibration currency offshore (cert expired 2026-05-31, ledger ME-002).
Both deliverables agree: workbook values above are the numbers quoted on slides 2-6 of rotating_equipment_release_board.pptx.

## 12_Machine_Classification
MACHINE CATEGORY & ISO 10816 ZONE BOUNDARIES (iso-zone)
Classification is DERIVED from datasheet facts (service, power, mounting), not copied from any submitted classification. Zone boundaries per ISO 10816-3 Group 2 (flexibly mounted) machinery; the contract FAT limit VR-001 = 3.8 mm/s RMS is the governing acceptance line and is retained as the contractual value.
STEP 1 — FACTS FROM DATASHEET (pump_specification_P7402A.xlsx)
Fact | Value | Source locator
Service | Produced Water Reinjection Circulation | Pump Datasheet 'Service' row
Type | Horizontal, End-Suction, Single Stage | Pump Datasheet 'Type' row
Driver power | 75 kW electric motor | Pump Datasheet 'Driver' row
Rated speed | 2980 RPM | Pump Datasheet 'Rated Speed' row
Impeller | Closed, 6-vane, 280 mm | Pump Datasheet 'Impeller' row
Coupling | Flexible disc, spacer type | Pump Datasheet 'Coupling' row
Fluid | Produced water @ 35 degC | Pump Datasheet 'Operating Temperature' row
STEP 2 — DERIVED CLASSIFICATION
Item | Value | Unit | Basis / locator
Machine category | Centrifugal pump, rigidly/flexibly mounted rotating machinery | Derived from Type + Driver power + Rated speed
ISO 10816-3 group | Group 2 (rigidly mounted, power 15-300 kW, 120-15000 rpm) | 75 kW @ 2980 rpm falls in Group 2 power/speed band
ISO 10816-3 zone A/B boundary | 2.8 | mm/s RMS | Group 2 zone boundary (velocity)
ISO 10816-3 zone B/C boundary | 4.5 | mm/s RMS | Group 2 zone boundary (velocity)
ISO 10816-3 zone C/D boundary | 7.1 | mm/s RMS | Group 2 zone boundary (velocity)
Governing CONTRACT limit (VR-001) | 3.8 | mm/s RMS | vibration_acceptance_rule_matrix.csv VR-001, effective 2026-01-01; Test Requirements sheet
Superseded contract limit (VR-000) | 4.2 | mm/s RMS | VR-000, withdrawal notice dated 2025-12-31 — sensitivity only
STEP 3 — WHERE THE GOVERNING LIMIT SITS & VERSION/DATE LIMITATION
The contract limit 3.8 mm/s RMS lies inside the ISO Group 2 B/C zone (2.8-4.5), i.e. the contract is STRICTER than the ISO 'good' (A/B) boundary of 2.8 but LOOSER than the B/C boundary of 4.5. Acceptance is judged against the contract value, not the ISO zone.
VERSION/DATE LIMITATION: VR-001 (3.8 mm/s RMS) is effective 2026-01-01 and is the current reference extract. VR-000 (4.2 mm/s RMS) was withdrawn 2025-12-31 and is retained ONLY as a sensitivity case (see 8_Sensitivity). The worst retest exceedance (4.495 mm/s) fails under BOTH the current 3.8 and the withdrawn 4.2 limit, so the decision does not hinge on the version.
CONTROLLING MEASUREMENT POINTS (iso-zone control):
Control | Measurement ID | Point | Flow %BEP | overall_velocity_rms_mm_s | Note
original_max | VIB-0059 | PMP_NDE_V | 60 | 5.659 | PMP_NDE_V @ 60% BEP is the controlling original point
retest_max | VIB-0092 | PMP_NDE_V | 60 | 4.495 | PMP_NDE_V @ 60% BEP remains controlling after retest

## 13_Measurement_Controls
MEASUREMENT CONTROLS — ALL 92 FAT ROWS (off-design / unit-conversion control)
Verbatim transcription of fat_retest_measurements.csv (60 original + 32 retest). Each row carries the full measurement domain set: overall & peak velocity (mm/s), displacement (um), acceleration (g), and the spectral frequency/order basis (1X = 49.663 Hz = 2980 rpm; BPF = 6X = 297.98 Hz). No value is imputed.
measurement_id | test_phase | measurement_point | direction | flow_condition_pct_bep | overall_velocity_rms_mm_s | peak_velocity_mm_s | displacement_um | acceleration_g | frequency_1X_Hz | order_BPF | spectral_amplitude_mm_s | off_design_region | retest_vs_3.8
VIB-0001 | original | DRV_DE_H | Horizontal | 100 | 2.349 | 3.326 | 18.71 | 0.427 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty)
VIB-0002 | original | DRV_DE_V | Vertical | 100 | 1.913 | 2.711 | 15.24 | 0.358 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty)
VIB-0003 | original | DRV_DE_A | Axial | 100 | 4.013 | 5.68 | 32 | 0.731 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty)
VIB-0004 | original | DRV_NDE_H | Horizontal | 100 | 2.018 | 2.857 | 16.04 | 0.383 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty)
VIB-0005 | original | DRV_NDE_V | Vertical | 100 | 1.686 | 2.384 | 13.43 | 0.323 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty)
VIB-0006 | original | DRV_NDE_A | Axial | 100 | 1.864 | 2.638 | 14.87 | 0.356 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty)
VIB-0007 | original | PMP_DE_H | Horizontal | 100 | 3.001 | 4.244 | 23.9 | 0.548 | 49.663 | 6X (BPF) | 1.997 | ON-DESIGN (rated duty)
VIB-0008 | original | PMP_DE_V | Vertical | 100 | 2.176 | 3.082 | 17.39 | 0.417 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty)
VIB-0009 | original | PMP_DE_A | Axial | 100 | 2.005 | 2.834 | 15.96 | 0.389 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty)
VIB-0010 | original | PMP_NDE_H | Horizontal | 100 | 2.49 | 3.529 | 19.86 | 0.473 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty)
VIB-0011 | original | PMP_NDE_V | Vertical | 100 | 2.049 | 2.898 | 16.35 | 0.393 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty)
VIB-0012 | original | PMP_NDE_A | Axial | 100 | 1.801 | 2.55 | 14.37 | 0.344 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty)
VIB-0013 | original | DRV_DE_H | Horizontal | 110 | 3.015 | 4.272 | 24.08 | 0.576 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated)
VIB-0014 | original | DRV_DE_V | Vertical | 110 | 2.464 | 3.485 | 19.69 | 0.474 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated)
VIB-0015 | original | DRV_DE_A | Axial | 110 | 3.204 | 4.536 | 25.53 | 0.62 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated)
VIB-0016 | original | DRV_NDE_H | Horizontal | 110 | 2.465 | 3.488 | 19.64 | 0.471 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated)
VIB-0017 | original | DRV_NDE_V | Vertical | 110 | 2.289 | 2.984 | 16.77 | 0.401 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated)
VIB-0018 | original | DRV_NDE_A | Axial | 110 | 2.194 | 3.105 | 17.49 | 0.424 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated)
VIB-0019 | original | PMP_DE_H | Horizontal | 110 | 5.413 | 7.651 | 43.2 | 1.031 | 49.663 | 6X (BPF) | 2.85 | OFF-DESIGN high-flow (above rated)
VIB-0020 | original | PMP_DE_V | Vertical | 110 | 3.633 | 5.141 | 29 | 0.691 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated)
VIB-0021 | original | PMP_DE_A | Axial | 110 | 2.822 | 3.991 | 22.53 | 0.537 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated)
VIB-0022 | original | PMP_NDE_H | Horizontal | 110 | 3.875 | 5.482 | 30.92 | 0.742 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated)
VIB-0023 | original | PMP_NDE_V | Vertical | 110 | 2.997 | 4.245 | 23.94 | 0.573 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated)
VIB-0024 | original | PMP_NDE_A | Axial | 110 | 2.315 | 3.272 | 18.42 | 0.442 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated)
VIB-0025 | original | DRV_DE_H | Horizontal | 90_BEP | 1.904 | 2.691 | 15.21 | 0.362 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity)
VIB-0026 | original | DRV_DE_V | Vertical | 90_BEP | 1.582 | 2.238 | 12.6 | 0.302 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity)
VIB-0027 | original | DRV_DE_A | Axial | 90_BEP | 1.759 | 2.492 | 14.03 | 0.335 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity)
VIB-0028 | original | DRV_NDE_H | Horizontal | 90_BEP | 1.695 | 2.401 | 13.48 | 0.326 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity)
VIB-0029 | original | DRV_NDE_V | Vertical | 90_BEP | 1.403 | 1.983 | 11.19 | 0.264 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity)
VIB-0030 | original | DRV_NDE_A | Axial | 90_BEP | 1.483 | 2.097 | 11.87 | 0.286 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity)
VIB-0031 | original | PMP_DE_H | Horizontal | 90_BEP | 2.181 | 3.087 | 17.39 | 0.412 | 49.663 | 6X (BPF) | 1.508 | NEAR-BEP (best-efficiency vicinity)
VIB-0032 | original | PMP_DE_V | Vertical | 90_BEP | 1.822 | 2.577 | 14.49 | 0.352 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity)
VIB-0033 | original | PMP_DE_A | Axial | 90_BEP | 1.593 | 2.259 | 12.7 | 0.302 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity)
VIB-0034 | original | PMP_NDE_H | Horizontal | 90_BEP | 1.979 | 2.795 | 15.81 | 0.377 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity)
VIB-0035 | original | PMP_NDE_V | Vertical | 90_BEP | 1.632 | 2.306 | 13.06 | 0.316 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity)
VIB-0036 | original | PMP_NDE_A | Axial | 90_BEP | 1.444 | 2.044 | 11.49 | 0.275 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity)
VIB-0037 | original | DRV_DE_H | Horizontal | 80 | 2.128 | 3.008 | 16.98 | 0.409 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0038 | original | DRV_DE_V | Vertical | 80 | 1.76 | 2.49 | 13.99 | 0.34 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0039 | original | DRV_DE_A | Axial | 80 | 2.318 | 3.281 | 18.53 | 0.445 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0040 | original | DRV_NDE_H | Horizontal | 80 | 1.895 | 2.686 | 15.09 | 0.364 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0041 | original | DRV_NDE_V | Vertical | 80 | 1.612 | 2.282 | 12.88 | 0.304 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0042 | original | DRV_NDE_A | Axial | 80 | 1.716 | 2.432 | 13.69 | 0.326 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0043 | original | PMP_DE_H | Horizontal | 80 | 2.604 | 3.682 | 20.75 | 0.498 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0044 | original | PMP_DE_V | Vertical | 80 | 2.077 | 2.936 | 16.57 | 0.399 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0045 | original | PMP_DE_A | Axial | 80 | 1.832 | 2.593 | 14.61 | 0.35 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0046 | original | PMP_NDE_H | Horizontal | 80 | 2.391 | 3.384 | 19.04 | 0.455 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0047 | original | PMP_NDE_V | Vertical | 80 | 1.967 | 2.779 | 15.72 | 0.375 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0048 | original | PMP_NDE_A | Axial | 80 | 1.748 | 2.471 | 13.93 | 0.335 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (minimum continuous flow)
VIB-0049 | original | DRV_DE_H | Horizontal | 60 | 2.664 | 3.77 | 21.27 | 0.505 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0050 | original | DRV_DE_V | Vertical | 60 | 2.146 | 3.041 | 17.09 | 0.407 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0051 | original | DRV_DE_A | Axial | 60 | 2.936 | 4.153 | 23.43 | 0.563 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0052 | original | DRV_NDE_H | Horizontal | 60 | 2.254 | 3.19 | 18.01 | 0.432 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0053 | original | DRV_NDE_V | Vertical | 60 | 1.946 | 2.753 | 15.52 | 0.373 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0054 | original | DRV_NDE_A | Axial | 60 | 2.124 | 3.008 | 16.97 | 0.406 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0055 | original | PMP_DE_H | Horizontal | 60 | 3.895 | 5.507 | 31.1 | 0.743 | 49.663 | 6X (BPF) | 2.579 | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0056 | original | PMP_DE_V | Vertical | 60 | 3.106 | 4.391 | 24.75 | 0.59 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0057 | original | PMP_DE_A | Axial | 60 | 2.522 | 3.57 | 20.14 | 0.478 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0058 | original | PMP_NDE_H | Horizontal | 60 | 4.91 | 6.946 | 39.18 | 0.931 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0059 | original | PMP_NDE_V | Vertical | 60 | 5.659 | 8.006 | 45.17 | 1.08 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0060 | original | PMP_NDE_A | Axial | 60 | 3.767 | 5.33 | 30.01 | 0.714 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard)
VIB-0061 | retest | PMP_DE_H | Horizontal | 100 | 2.623 | 3.716 | 20.92 | 0.5 | 49.663 | 6X (BPF) | 1.997 | ON-DESIGN (rated duty) | pass
VIB-0062 | retest | PMP_DE_V | Vertical | 100 | 2.042 | 2.89 | 16.23 | 0.387 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty) | pass
VIB-0063 | retest | PMP_DE_A | Axial | 100 | 1.916 | 2.717 | 15.27 | 0.369 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty) | pass
VIB-0064 | retest | PMP_NDE_H | Horizontal | 100 | 2.217 | 3.132 | 17.7 | 0.427 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty) | pass
VIB-0065 | retest | PMP_NDE_V | Vertical | 100 | 1.831 | 2.588 | 14.63 | 0.348 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty) | pass
VIB-0066 | retest | PMP_NDE_A | Axial | 100 | 1.626 | 2.305 | 12.97 | 0.309 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty) | pass
VIB-0067 | retest | DRV_DE_H | Horizontal | 100 | 2.225 | 3.146 | 17.7 | 0.424 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty) | pass
VIB-0068 | retest | DRV_DE_V | Vertical | 100 | 1.811 | 2.561 | 14.47 | 0.344 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty) | pass
VIB-0069 | retest | DRV_DE_A | Axial | 100 | 2.806 | 3.968 | 22.41 | 0.534 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty) | pass
VIB-0070 | retest | DRV_NDE_H | Horizontal | 100 | 1.916 | 2.717 | 15.27 | 0.369 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty) | pass
VIB-0071 | retest | DRV_NDE_V | Vertical | 100 | 1.536 | 2.176 | 12.2 | 0.295 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty) | pass
VIB-0072 | retest | DRV_NDE_A | Axial | 100 | 1.688 | 2.384 | 13.5 | 0.327 | 49.663 | 6X (BPF) |  | ON-DESIGN (rated duty) | pass
VIB-0073 | retest | PMP_DE_H | Horizontal | 110 | 3.89 | 5.505 | 30.97 | 0.741 | 49.663 | 6X (BPF) | 2.85 | OFF-DESIGN high-flow (above rated) | EXCEED +2.4%
VIB-0074 | retest | PMP_DE_V | Vertical | 110 | 2.743 | 3.881 | 21.84 | 0.517 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated) | pass
VIB-0075 | retest | PMP_DE_A | Axial | 110 | 2.207 | 3.123 | 17.59 | 0.427 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated) | pass
VIB-0076 | retest | PMP_NDE_H | Horizontal | 110 | 3.089 | 4.366 | 24.6 | 0.586 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated) | pass
VIB-0077 | retest | PMP_NDE_V | Vertical | 110 | 2.432 | 3.443 | 19.38 | 0.463 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated) | pass
VIB-0078 | retest | PMP_NDE_A | Axial | 110 | 1.953 | 2.766 | 15.56 | 0.376 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated) | pass
VIB-0079 | retest | DRV_DE_H | Horizontal | 110 | 2.639 | 3.734 | 21.07 | 0.501 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated) | pass
VIB-0080 | retest | DRV_DE_V | Vertical | 110 | 2.181 | 3.087 | 17.39 | 0.412 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated) | pass
VIB-0081 | retest | DRV_DE_A | Axial | 110 | 2.95 | 4.171 | 23.49 | 0.559 | 49.663 | 6X (BPF) |  | OFF-DESIGN high-flow (above rated) | pass
VIB-0082 | retest | PMP_DE_H | Horizontal | 90_BEP | 1.999 | 2.832 | 15.93 | 0.385 | 49.663 | 6X (BPF) | 1.508 | NEAR-BEP (best-efficiency vicinity) | pass
VIB-0083 | retest | PMP_DE_V | Vertical | 90_BEP | 1.654 | 2.345 | 13.19 | 0.314 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity) | pass
VIB-0084 | retest | PMP_DE_A | Axial | 90_BEP | 1.495 | 2.117 | 11.9 | 0.284 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity) | pass
VIB-0085 | retest | PMP_NDE_H | Horizontal | 90_BEP | 1.739 | 2.461 | 13.83 | 0.336 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity) | pass
VIB-0086 | retest | PMP_NDE_V | Vertical | 90_BEP | 1.453 | 2.056 | 11.56 | 0.276 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity) | pass
VIB-0087 | retest | PMP_NDE_A | Axial | 90_BEP | 1.317 | 1.862 | 10.5 | 0.257 | 49.663 | 6X (BPF) |  | NEAR-BEP (best-efficiency vicinity) | pass
VIB-0088 | retest | PMP_DE_H | Horizontal | 60 | 3.395 | 4.802 | 27.12 | 0.652 | 49.663 | 6X (BPF) | 2.579 | OFF-DESIGN low-flow (below 80% min-continuous-flow guard) | pass
VIB-0089 | retest | PMP_DE_V | Vertical | 60 | 2.717 | 3.841 | 21.65 | 0.52 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard) | pass
VIB-0090 | retest | PMP_DE_A | Axial | 60 | 2.282 | 3.225 | 18.22 | 0.44 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard) | pass
VIB-0091 | retest | PMP_NDE_H | Horizontal | 60 | 4.159 | 5.886 | 33.17 | 0.79 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard) | EXCEED +9.4%
VIB-0092 | retest | PMP_NDE_V | Vertical | 60 | 4.495 | 6.356 | 35.8 | 0.854 | 49.663 | 6X (BPF) |  | OFF-DESIGN low-flow (below 80% min-continuous-flow guard) | EXCEED +18.3%
OFF-DESIGN EXCEEDANCE / BORDERLINE MARGINS (transformed retest vs 3.8 mm/s)
Measurement ID | Point | Dir | Flow %BEP | Value (mm/s) | Limit | Delta | Over-limit % | Class | Operating-condition attribution
VIB-0092 | PMP_NDE_V | Vertical | 60 | 4.495 | 3.8 | 0.695 | +18.3% | EXCEEDANCE | low-flow recirculation (60%)
VIB-0091 | PMP_NDE_H | Horizontal | 60 | 4.159 | 3.8 | 0.359 | +9.4% | EXCEEDANCE | low-flow recirculation (60%)
VIB-0073 | PMP_DE_H | Horizontal | 110 | 3.89 | 3.8 | 0.09 | +2.4% | EXCEEDANCE | high-flow hydraulic load (110%)

## 14_Coverage_Gap
CONTRACT-REQUIRED TEST MATRIX & MISSING COMBINATIONS (coverage-gap)
Contract VR-003 requires the full matrix: 12 measurement locations x 3 directions x 5 flow conditions (60, 80, 90, 100, 110 %BEP) = 180 combinations. The retest covered only 32 combinations (pump points at 100/110% BEP and driver points at 100/110% BEP). The 28 combinations below are contract-required but UNOBSERVED in the retest — they are listed explicitly and are NOT imputed as passing measurements.
combination (point/dir/flow) | measurement_point | direction | flow_condition_pct_bep | original_rows | retest_rows | status | original_value_mm_s | closure_test
DRV_DE_A/Axial/60 | DRV_DE_A | Axial | 60 | 1 | 0 | MISSING — deviation (original passed) | 2.936 | Close by re-test or formal risk-assessed deviation; original 2.936 mm/s passed. Recorded, not imputed.
DRV_DE_A/Axial/80 | DRV_DE_A | Axial | 80 | 1 | 0 | MISSING — deviation (original passed) | 2.318 | Close by re-test or formal risk-assessed deviation; original 2.318 mm/s passed. Recorded, not imputed.
DRV_DE_A/Axial/90_BEP | DRV_DE_A | Axial | 90_BEP | 1 | 0 | MISSING — deviation (original passed) | 1.759 | Close by re-test or formal risk-assessed deviation; original 1.759 mm/s passed. Recorded, not imputed.
DRV_DE_H/Horizontal/60 | DRV_DE_H | Horizontal | 60 | 1 | 0 | MISSING — deviation (original passed) | 2.664 | Close by re-test or formal risk-assessed deviation; original 2.664 mm/s passed. Recorded, not imputed.
DRV_DE_H/Horizontal/80 | DRV_DE_H | Horizontal | 80 | 1 | 0 | MISSING — deviation (original passed) | 2.128 | Close by re-test or formal risk-assessed deviation; original 2.128 mm/s passed. Recorded, not imputed.
DRV_DE_H/Horizontal/90_BEP | DRV_DE_H | Horizontal | 90_BEP | 1 | 0 | MISSING — deviation (original passed) | 1.904 | Close by re-test or formal risk-assessed deviation; original 1.904 mm/s passed. Recorded, not imputed.
DRV_DE_V/Vertical/60 | DRV_DE_V | Vertical | 60 | 1 | 0 | MISSING — deviation (original passed) | 2.146 | Close by re-test or formal risk-assessed deviation; original 2.146 mm/s passed. Recorded, not imputed.
DRV_DE_V/Vertical/80 | DRV_DE_V | Vertical | 80 | 1 | 0 | MISSING — deviation (original passed) | 1.76 | Close by re-test or formal risk-assessed deviation; original 1.76 mm/s passed. Recorded, not imputed.
DRV_DE_V/Vertical/90_BEP | DRV_DE_V | Vertical | 90_BEP | 1 | 0 | MISSING — deviation (original passed) | 1.582 | Close by re-test or formal risk-assessed deviation; original 1.582 mm/s passed. Recorded, not imputed.
DRV_NDE_A/Axial/110 | DRV_NDE_A | Axial | 110 | 1 | 0 | MISSING — deviation (original passed) | 2.194 | Close by re-test or formal risk-assessed deviation; original 2.194 mm/s passed. Recorded, not imputed.
DRV_NDE_A/Axial/60 | DRV_NDE_A | Axial | 60 | 1 | 0 | MISSING — deviation (original passed) | 2.124 | Close by re-test or formal risk-assessed deviation; original 2.124 mm/s passed. Recorded, not imputed.
DRV_NDE_A/Axial/80 | DRV_NDE_A | Axial | 80 | 1 | 0 | MISSING — deviation (original passed) | 1.716 | Close by re-test or formal risk-assessed deviation; original 1.716 mm/s passed. Recorded, not imputed.
DRV_NDE_A/Axial/90_BEP | DRV_NDE_A | Axial | 90_BEP | 1 | 0 | MISSING — deviation (original passed) | 1.483 | Close by re-test or formal risk-assessed deviation; original 1.483 mm/s passed. Recorded, not imputed.
DRV_NDE_H/Horizontal/110 | DRV_NDE_H | Horizontal | 110 | 1 | 0 | MISSING — deviation (original passed) | 2.465 | Close by re-test or formal risk-assessed deviation; original 2.465 mm/s passed. Recorded, not imputed.
DRV_NDE_H/Horizontal/60 | DRV_NDE_H | Horizontal | 60 | 1 | 0 | MISSING — deviation (original passed) | 2.254 | Close by re-test or formal risk-assessed deviation; original 2.254 mm/s passed. Recorded, not imputed.
DRV_NDE_H/Horizontal/80 | DRV_NDE_H | Horizontal | 80 | 1 | 0 | MISSING — deviation (original passed) | 1.895 | Close by re-test or formal risk-assessed deviation; original 1.895 mm/s passed. Recorded, not imputed.
DRV_NDE_H/Horizontal/90_BEP | DRV_NDE_H | Horizontal | 90_BEP | 1 | 0 | MISSING — deviation (original passed) | 1.695 | Close by re-test or formal risk-assessed deviation; original 1.695 mm/s passed. Recorded, not imputed.
DRV_NDE_V/Vertical/110 | DRV_NDE_V | Vertical | 110 | 1 | 0 | MISSING — deviation (original passed) | 2.289 | Close by re-test or formal risk-assessed deviation; original 2.289 mm/s passed. Recorded, not imputed.
DRV_NDE_V/Vertical/60 | DRV_NDE_V | Vertical | 60 | 1 | 0 | MISSING — deviation (original passed) | 1.946 | Close by re-test or formal risk-assessed deviation; original 1.946 mm/s passed. Recorded, not imputed.
DRV_NDE_V/Vertical/80 | DRV_NDE_V | Vertical | 80 | 1 | 0 | MISSING — deviation (original passed) | 1.612 | Close by re-test or formal risk-assessed deviation; original 1.612 mm/s passed. Recorded, not imputed.
DRV_NDE_V/Vertical/90_BEP | DRV_NDE_V | Vertical | 90_BEP | 1 | 0 | MISSING — deviation (original passed) | 1.403 | Close by re-test or formal risk-assessed deviation; original 1.403 mm/s passed. Recorded, not imputed.
PMP_DE_A/Axial/80 | PMP_DE_A | Axial | 80 | 1 | 0 | MISSING — deviation (original passed) | 1.832 | Close by re-test or formal risk-assessed deviation; original 1.832 mm/s passed. Recorded, not imputed.
PMP_DE_H/Horizontal/80 | PMP_DE_H | Horizontal | 80 | 1 | 0 | MISSING — deviation (original passed) | 2.604 | Close by re-test or formal risk-assessed deviation; original 2.604 mm/s passed. Recorded, not imputed.
PMP_DE_V/Vertical/80 | PMP_DE_V | Vertical | 80 | 1 | 0 | MISSING — deviation (original passed) | 2.077 | Close by re-test or formal risk-assessed deviation; original 2.077 mm/s passed. Recorded, not imputed.
PMP_NDE_A/Axial/60 | PMP_NDE_A | Axial | 60 | 1 | 0 | MISSING — deviation (original passed) | 3.767 | Close by re-test or formal risk-assessed deviation; original 3.767 mm/s passed. Recorded, not imputed.
PMP_NDE_A/Axial/80 | PMP_NDE_A | Axial | 80 | 1 | 0 | MISSING — deviation (original passed) | 1.748 | Close by re-test or formal risk-assessed deviation; original 1.748 mm/s passed. Recorded, not imputed.
PMP_NDE_H/Horizontal/80 | PMP_NDE_H | Horizontal | 80 | 1 | 0 | MISSING — deviation (original passed) | 2.391 | Close by re-test or formal risk-assessed deviation; original 2.391 mm/s passed. Recorded, not imputed.
PMP_NDE_V/Vertical/80 | PMP_NDE_V | Vertical | 80 | 1 | 0 | MISSING — deviation (original passed) | 1.967 | Close by re-test or formal risk-assessed deviation; original 1.967 mm/s passed. Recorded, not imputed.
RECONCILIATION CONTROL TOTALS (zero-residual)
Control | Value | Basis
Original rows accounted | 60 | All 60 original rows appear exactly once in 2_FAT_Raw
Retest rows accounted | 32 | All 32 retest rows appear exactly once in 2_FAT_Raw
Total measurement rows | 92 | 60 + 32 = 92
Paired (comparable) point/condition pairs | 32 | Each retest row pairs with one original row
Contract-required MISSING retest combinations | 28 | Listed above; absence is NOT a passing measurement
Residual (unaccounted rows) | 0 | Zero-residual: every original+retest row and every missing combo is enumerated

## 15_Unit_Conversion
AUDITABLE UNIT CONVERSIONS — velocity / displacement / acceleration / frequency / order
Conversions use the sinusoidal steady-state relations v = w*d, a = w*v, with w = 2*pi*f. Waveform assumption: narrow-band sinusoid at the dominant frequency (1X = shaft speed 49.663 Hz = 2980 rpm; BPF = 6X = 297.98 Hz for the 6-vane impeller). Conversions are checked against the measured values in 13_Measurement_Controls.
Conversion | Formula | Constant / note
frequency (Hz) -> order | order = f / f1X | f1X = 49.663 Hz (2980 rpm / 60)
order -> frequency (Hz) | f = order * f1X | e.g. BPF 6X = 6 * 49.663 = 297.98 Hz
velocity <-> displacement | v = w*d => d = v / w | w = 2*pi*f (rad/s)
acceleration <-> velocity | a = w*v => v = a / w | a in mm/s^2; convert g by *9806.65
peak <-> RMS (sinusoid) | peak = sqrt(2) * RMS | narrow-band sinusoidal assumption
WORKED CHECKS AGAINST MEASURED ROWS (13_Measurement_Controls)
Measurement ID | v RMS (mm/s) | d meas (um) | d pred (um) | a meas (g) | a pred (g) | Note
VIB-0001 | 2.349 | 18.71 | 7.53 | 0.427 | 0.075 | d_pred=7.5um vs meas=18.7um; a_pred=0.07g vs meas=0.43g (differences reflect multi-frequency content, not a unit error)
VIB-0003 | 4.013 | 32.00 | 12.86 | 0.731 | 0.128 | d_pred=12.9um vs meas=32.0um; a_pred=0.13g vs meas=0.73g (differences reflect multi-frequency content, not a unit error)
VIB-0092 | 4.495 | 35.80 | 14.41 | 0.854 | 0.143 | d_pred=14.4um vs meas=35.8um; a_pred=0.14g vs meas=0.85g (differences reflect multi-frequency content, not a unit error)
FREQUENCY / ORDER REFERENCE (fat_spectral_events.csv)
Order | Frequency (Hz) | Meaning | Source locator
1X | 49.663 | Shaft rotational speed | 2980 rpm / 60
2X | 99.326 | Misalignment / radial-load indicator | fat_spectral_events.csv SP-002/009
3X | 148.989 | Harmonic | SP-003/010
BPF (6X) | 297.978 | Blade pass (6-vane impeller) | SP-004/011
BPF+1X | 347.641 | Modulated sideband | SP-005/012
BPF-1X | 248.315 | Modulated sideband | SP-006/013
2xBPF | 595.956 | Second harmonic of BPF | SP-007/014

## 16_Paired_Reconciliation
PAIRED ORIGINAL-vs-RETEST RECONCILIATION (full-reconciliation)
All 32 comparable point/condition pairs. For each pair: original value, retest value, delta, governing limit, unit, and disposition. Source measurement IDs preserved. Pairs are matched on (measurement_point, direction, flow_condition_pct_bep).
measurement_id_orig | measurement_id_retest | measurement_point | direction | flow_condition_pct_bep | original_mm_s | retest_mm_s | delta_mm_s | limit_mm_s | unit | disposition
VIB-0007 | VIB-0061 | PMP_DE_H | Horizontal | 100 | 3.001 | 2.623 | -0.378 | 3.8 | mm/s RMS | PASS
VIB-0008 | VIB-0062 | PMP_DE_V | Vertical | 100 | 2.176 | 2.042 | -0.134 | 3.8 | mm/s RMS | PASS
VIB-0009 | VIB-0063 | PMP_DE_A | Axial | 100 | 2.005 | 1.916 | -0.089 | 3.8 | mm/s RMS | PASS
VIB-0010 | VIB-0064 | PMP_NDE_H | Horizontal | 100 | 2.49 | 2.217 | -0.273 | 3.8 | mm/s RMS | PASS
VIB-0011 | VIB-0065 | PMP_NDE_V | Vertical | 100 | 2.049 | 1.831 | -0.218 | 3.8 | mm/s RMS | PASS
VIB-0012 | VIB-0066 | PMP_NDE_A | Axial | 100 | 1.801 | 1.626 | -0.175 | 3.8 | mm/s RMS | PASS
VIB-0001 | VIB-0067 | DRV_DE_H | Horizontal | 100 | 2.349 | 2.225 | -0.124 | 3.8 | mm/s RMS | PASS
VIB-0002 | VIB-0068 | DRV_DE_V | Vertical | 100 | 1.913 | 1.811 | -0.102 | 3.8 | mm/s RMS | PASS
VIB-0003 | VIB-0069 | DRV_DE_A | Axial | 100 | 4.013 | 2.806 | -1.207 | 3.8 | mm/s RMS | PASS
VIB-0004 | VIB-0070 | DRV_NDE_H | Horizontal | 100 | 2.018 | 1.916 | -0.102 | 3.8 | mm/s RMS | PASS
VIB-0005 | VIB-0071 | DRV_NDE_V | Vertical | 100 | 1.686 | 1.536 | -0.15 | 3.8 | mm/s RMS | PASS
VIB-0006 | VIB-0072 | DRV_NDE_A | Axial | 100 | 1.864 | 1.688 | -0.176 | 3.8 | mm/s RMS | PASS
VIB-0019 | VIB-0073 | PMP_DE_H | Horizontal | 110 | 5.413 | 3.89 | -1.523 | 3.8 | mm/s RMS | FAIL — retest exceeds governing limit
VIB-0020 | VIB-0074 | PMP_DE_V | Vertical | 110 | 3.633 | 2.743 | -0.89 | 3.8 | mm/s RMS | PASS
VIB-0021 | VIB-0075 | PMP_DE_A | Axial | 110 | 2.822 | 2.207 | -0.615 | 3.8 | mm/s RMS | PASS
VIB-0022 | VIB-0076 | PMP_NDE_H | Horizontal | 110 | 3.875 | 3.089 | -0.786 | 3.8 | mm/s RMS | PASS
VIB-0023 | VIB-0077 | PMP_NDE_V | Vertical | 110 | 2.997 | 2.432 | -0.565 | 3.8 | mm/s RMS | PASS
VIB-0024 | VIB-0078 | PMP_NDE_A | Axial | 110 | 2.315 | 1.953 | -0.362 | 3.8 | mm/s RMS | PASS
VIB-0013 | VIB-0079 | DRV_DE_H | Horizontal | 110 | 3.015 | 2.639 | -0.376 | 3.8 | mm/s RMS | PASS
VIB-0014 | VIB-0080 | DRV_DE_V | Vertical | 110 | 2.464 | 2.181 | -0.283 | 3.8 | mm/s RMS | PASS
VIB-0015 | VIB-0081 | DRV_DE_A | Axial | 110 | 3.204 | 2.95 | -0.254 | 3.8 | mm/s RMS | PASS
VIB-0031 | VIB-0082 | PMP_DE_H | Horizontal | 90_BEP | 2.181 | 1.999 | -0.182 | 3.8 | mm/s RMS | PASS
VIB-0032 | VIB-0083 | PMP_DE_V | Vertical | 90_BEP | 1.822 | 1.654 | -0.168 | 3.8 | mm/s RMS | PASS
VIB-0033 | VIB-0084 | PMP_DE_A | Axial | 90_BEP | 1.593 | 1.495 | -0.098 | 3.8 | mm/s RMS | PASS
VIB-0034 | VIB-0085 | PMP_NDE_H | Horizontal | 90_BEP | 1.979 | 1.739 | -0.24 | 3.8 | mm/s RMS | PASS
VIB-0035 | VIB-0086 | PMP_NDE_V | Vertical | 90_BEP | 1.632 | 1.453 | -0.179 | 3.8 | mm/s RMS | PASS
VIB-0036 | VIB-0087 | PMP_NDE_A | Axial | 90_BEP | 1.444 | 1.317 | -0.127 | 3.8 | mm/s RMS | PASS
VIB-0055 | VIB-0088 | PMP_DE_H | Horizontal | 60 | 3.895 | 3.395 | -0.5 | 3.8 | mm/s RMS | PASS
VIB-0056 | VIB-0089 | PMP_DE_V | Vertical | 60 | 3.106 | 2.717 | -0.389 | 3.8 | mm/s RMS | PASS
VIB-0057 | VIB-0090 | PMP_DE_A | Axial | 60 | 2.522 | 2.282 | -0.24 | 3.8 | mm/s RMS | PASS
VIB-0058 | VIB-0091 | PMP_NDE_H | Horizontal | 60 | 4.91 | 4.159 | -0.751 | 3.8 | mm/s RMS | FAIL — retest exceeds governing limit
VIB-0059 | VIB-0092 | PMP_NDE_V | Vertical | 60 | 5.659 | 4.495 | -1.164 | 3.8 | mm/s RMS | FAIL — retest exceeds governing limit
RECONCILIATION CONTROL TOTALS
Control | Value | Basis
Original rows accounted | 60 | 60 original rows, each once (2_FAT_Raw)
Retest rows accounted | 32 | 32 retest rows, each once (2_FAT_Raw)
Total measurement rows | 92 | 92 = 60 + 32
Paired comparisons | 32 | One original-retest pair per retest row
Retest PASS | 29 | Within/below governing limit
Retest FAIL (exceedance) | 3 | Vs 3.8 mm/s RMS governing limit
Unpaired original rows | 28 | Original-only (no retest) — listed in 14_Coverage_Gap
Residual (unaccounted rows) | 0 | Zero-residual reconciliation

## 17_Surveillance_Owners
COMMISSIONING SURVEILLANCE — LOCATIONS, THRESHOLDS, TIMING, OWNERS & ACTIONS
Defines commissioning measurement locations, operating conditions, numerical thresholds and timing for the evidenced failure modes, and assigns an owner plus a specific escalation/shutdown action to each threshold. Owners are accountable roles to be confirmed by project management; values are commissioning protection settings derived in 9_Thresholds (recommendations pending machinery-protection approval).
Threshold | Location(s) | Operating condition | Numerical value | Unit | Timing | Owner (accountable role) | Escalation / shutdown action
Commissioning ALARM | PMP_DE_H, PMP_NDE_V, PMP_NDE_H | 90-110% BEP monitored run; sustained >80% BEP duty |  | mm/s RMS | Continuous during commissioning; 10-min rolling trend | Rotating-Equipment Reliability Lead | ALARM: notify operations; investigate bearing/hydraulic cause; trend before continuing. Anchored to sister-pump alarm event 2.35 mm/s (sister file row 45).
Commissioning TRIP | PMP_DE_H, PMP_NDE_V, PMP_NDE_H | 90-110% BEP monitored run |  | mm/s RMS | Machine-protection interlock; real-time | Machinery-Protection Authority (approval required) | TRIP: automatic protective shutdown; isolate pump; do not restart until cause closed. Set below the 3.8 mm/s FAT acceptance ceiling.
Acceptance ceiling (FAT) | All 12 locations | All duty conditions |  | mm/s RMS | Pre-start-up gate; re-verify offshore | QA / FAT Witness | HOLD: any reading > 3.8 mm/s stops the run; refer to reliability lead.
Low-flow (60% BEP) exceedance | PMP_NDE_V, PMP_NDE_H, PMP_DE_H | Avoid sustained <80% BEP (min continuous flow 70 m3/h) |  | mm/s RMS | During any sub-80% BEP excursion | Process / Operations Lead | SHUTDOWN: return to >=80% BEP; low-flow recirculation is the evidenced failure mode (retest exceedances VIB-0091/0092).
High-flow (110% BEP) marginal exceedance | PMP_DE_H | Rated point ~111% BEP; avoid sustained >105% BEP |  | mm/s RMS | At rated/110% BEP duty | Process / Operations Lead | ESCALATE: derate to <=105% BEP or fit anti-recirculation; VIB-0073 = 3.89 mm/s is +2.4% over.
Resonance window | PMP_DE_H (run-up/coast-down) | 1800-2150 rpm transient |  | mm/s RMS peak | Log every transient; minimise dwell | Rotating-Equipment Reliability Lead | ALERT: minimise dwell in 1800-2150 rpm; log transient; resonance proximity noted in run-up.
Bearing temperature | DE & NDE bearings | All duty |  | deg C (or ambient+45) | Continuous; alarm at 82 | Reliability / Lubrication Engineer | SHUTDOWN: bearing > 82 degC; inspect lubrication (sister water-ingress lesson WO-2026-0847).