## Slide 1
ROTATING EQUIPMENT RELEASE BOARD
P-7402A Produced Water Reinjection Pump
Post-Impeller Work · Repeat FAT Disposition
North Platform Reinjection Debottleneck | PO-2026-0742 | Model PWRI-220
Prepared by: Rotating-Equipment Reliability Lead | Date: 2026-09-02 | Workbook: fat_integrity_workbook.xlsx

## Slide 2
1. Executive Decision
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
DISPOSITION: CONDITIONAL RELEASE — Subject to 12 mandatory closure actions (C-01–C-12)
Recommendation
Release P-7402A for offshore commissioning under a defined set of field-verification gates and operating constraints. The repeat FAT after impeller work shows substantial improvement in the BEP region (90-100% BEP fully compliant) with marginal exceedances at 110% BEP (+2.4%) and material exceedances at 60% BEP (off-design radial-thrust region). Transient signature is acceptable with a 34% separation margin. Sister-pump baseline provides reference but baseline gap (~0.25 mm/s higher for P-7402A) must be closed in the field.
Material Exceptions (Non-compliant)
Rule | Point | Measured | Limit | Margin
VR-001 RMS | 110% PMP_DE_H | 3.89 mm/s | 3.80 | +0.09 (+2.4%)
VR-001 RMS | 60% PMP_NDE_H | 4.16 mm/s | 3.80 | +0.36 (+9.5%)
VR-001 RMS | 60% PMP_NDE_V | 4.50 mm/s | 3.80 | +0.70 (+18.3%)
VR-002 Peak | 110% BPF (SP-011) | 2.964 mm/s | 2.50 | +0.46 (+18.6%)
VR-002 Peak | 110% 1X (SP-008) | 2.85 mm/s | 2.50 | +0.35 (+14%)
Board Actions Required
▸ A-01 Confirm VR-001 (3.8 mm/s RMS) is governing contract limit
▸ A-02 Accept 10 material exceptions (E-01–E-10) with documented safeguards
▸ A-03 Authorize conditional release with 12 closure-action gates (C-01–C-12)
▸ A-04 Confirm sister-pump breather upgrade applied to P-7402A
Reference: fat_integrity_workbook.xlsx · Sheets: Disposition, FAT_Overall, FAT_Discrete, Discrepancy_Log

## Slide 3
2. Equipment & Scope
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
Parameter | Value | Unit
Tag / Model | P-7402A / PWRI-220 | 
Type | Horizontal End-Suction Single-Stage | 
Service | Produced Water Reinjection Circulation | 
Rated Flow / Head | 265 m³/h / 47.7 m | 
BEP Flow | 238.5 m³/h | 
Min Continuous Flow | 70 m³/h | 
Rated Speed | 2980 RPM | 
Driver | 75 kW, 380V, 50Hz Electric Motor | 
Impeller | 280 mm, Closed 6-vane, CF8M | 
Bearings DE/NDE | 6316 C3 / 6314 C3 DGBB | 
Mechanical Seal | Cartridge, API Plan 11 | 
Sister Pump | P-7402B (identical, commissioned 2025-06-20, 12840 hrs) | 
Scope of This Board
▸ Original FAT conducted 2026-05-12 (pre-impeller work)
▸ Impeller rework performed following elevated vibration at 60%/110% BEP
▸ Repeat FAT conducted 2026-05-15 (post-impeller work)
▸ Assessment covers: overall vibration (VR-001), discrete components (VR-002), transient (run-up/coast-down), sister-pump baseline, test coverage completeness
▸ Evidence claims from equipment_evidence_ledger.csv treated as submitted/contradicted/field-verification-required — not approved conclusions
▸ Governing rules extracted from vibration_acceptance_rule_matrix.csv with authority locators cited
Assumptions & Boundaries
▸ VR-001 (3.8 mm/s RMS) governs per effective date 2026-01-01; VR-000 (4.2) superseded
▸ Retest data is from same instrument setup as original FAT
▸ Sister-pump baseline (P-7402B) is representative of field-installed condition
▸ No performance/NPSH/hydrostatic retest data supplied — vibration scope only
▸ Contract limit authority (ME-001/009/017) is 'submitted' not 'verified' — board must confirm

## Slide 4
3. Governing Rules & Authority
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
Rule ID | Domain | Requirement | Limit | Authority | Status
VR-001 | Overall housing RMS | ≤ 3.8 mm/s RMS | 3.8 | API 610 Table 8 | GOVERNING (eff. 2026-01-01)
VR-002 | Discrete component peak | ≤ 2.5 mm/s peak | 2.5 | API 610 Table 8 | GOVERNING
VR-003 | FAT coverage | 60/90/100/110% BEP all points | — | Purchase spec | CONTRACT RECORD
VR-004 | Mechanical run time | ≥ 4 hours stable | 4 hr | API 610 Cl 8.3.4 | REFERENCE
VR-005 | Bearing temperature | ≤ 82°C or ambient+45 | 82°C | API 610 Cl 8.3.4 | REFERENCE
VR-006 | Shaft runout | ≤ 0.025 mm TIR | 0.025 | API 610 Cl 6.3 | REFERENCE
VR-007 | Instrument calibration | Certificate current | status | FAT quality plan | REFERENCE
VR-009/10 | Alarm / trip thresholds | Derived from baseline | derived | Standards matrix | COMMISSIONING
VR-011 | Missing retest closure | PMP_NDE_A @ 60% required | status | FAT test matrix | EVIDENCE GAP
VR-000 | Overall housing RMS | ≤ 4.2 mm/s RMS | 4.2 | API 610 Table 8 | SUPERSEDED (w/d 2025-12-31)
Key note: VR-000 (4.2 mm/s RMS) is explicitly marked 'superseded extract; withdrawal notice dated 2025-12-31' in the source matrix. It must NOT be used as the acceptance criterion. VR-001 (3.8 mm/s RMS, effective 2026-01-01) governs. However, the contract evidence rows ME-001/009/017 citing the 3.8 limit are in 'submitted' state — not independently verified by this board. Action A-01 requires the board to confirm authority from the purchase specification before final release.

## Slide 5
4. Evidence Register — State of Submitted Claims
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
equipment_evidence_ledger.csv — 24 evidence rows categorized by gate domain and state
Evidence State | Count | Examples | Board Implication
independently-verified | 6 | ME-002, ME-006, ME-010, ME-014, ME-018, ME-022 | Calibration, field baseline — can be relied upon
submitted | 6 | ME-001, ME-005, ME-009, ME-013, ME-017, ME-021 | Contract limit & maintenance history — NOT verified; must be confirmed
contradicted | 6 | ME-003, ME-007, ME-011, ME-015, ME-019, ME-023 | Baseplate level & shaft runout — requires field re-verification
field-verification-required | 6 | ME-004, ME-008, ME-012, ME-016, ME-020, ME-024 | Alignment & FAT test coverage — must close during commissioning
Critical Evidence Items
▸ ME-001/009/017 — Contract vibration limit 3.8 mm/s RMS: 'submitted' not 'verified'. This is the governing rule. Board must confirm authority (Action A-01).
▸ ME-007/015/023 — Shaft runout 0.021 mm TIR: within VR-006 limit (0.025) but 'contradicted'. Independent measurement required (Safeguard S-04).
▸ ME-003/011/019 — Baseplate level 0.08 mm/m: 'contradicted'. Field re-survey required post-grouting (Safeguard S-03).
▸ ME-004/012/020 — Cold alignment 0.045 mm offset: 'field-verification-required'. Hot alignment check mandatory (Safeguard S-02).
▸ ME-005/013/021 — P-7402B WO history 'water ingress': 'submitted'. Root cause is bearing lubrication contamination — drives breather upgrade (Safeguard S-05).

## Slide 6
5. FAT Overall Vibration — Original vs Retest
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
Chart: FAT Overall Vibration by Point — Original vs Retest vs VR-001 Limit (mm/s RMS)
| PMP_DE_H | PMP_DE_V | PMP_DE_A | PMP_NDE_H | PMP_NDE_V | PMP_NDE_A | DRV_DE_H | DRV_DE_V | DRV_DE_A | DRV_NDE_H | DRV_NDE_V | DRV_NDE_A
Original FAT (2026-05-12) | 3.001 | 2.176 | 2.005 | 2.49 | 2.049 | 1.801 | 2.349 | 1.913 | 4.013 | 2.018 | 1.686 | 1.864
Retest (2026-05-15) | 2.623 | 2.042 | 1.916 | 2.217 | 1.831 | 1.626 | 2.225 | 1.811 | 2.806 | 1.916 | 1.536 | 1.688
VR-001 Limit (3.8) | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8
100% BEP Summary (Rated Duty)
▸ Original max: 4.013 mm/s (DRV_DE_A, VIB-0003)
▸ Retest max: 2.806 mm/s (DRV_DE_A, VIB-0069)
▸ Improvement at DRV_DE_A: 1.207 mm/s (30%)
▸ All 12 points at 100% BEP COMPLIANT with VR-001
▸ DRV_DE_A margin: 3.80 - 2.806 = +0.994 mm/s
110% BEP (Overload)
▸ Original PMP_DE_H: 5.41 mm/s (FAIL)
▸ Retest PMP_DE_H: 3.89 mm/s (FAIL +0.09)
▸ Improvement: 1.52 mm/s (28%)
▸ Exceedance is marginal (+2.4%) but still non-compliant
▸ DRV_NDE retest data MISSING at 110% (coverage gap D-07)
Retest coverage: 32 of 180 contract-required combinations captured (VR-003 matrix: 12 points × 3 directions × 5 flows = 180; 17.8%). Missing: 28 combinations (all DRV at 60/80/90/110; PMP at 60/80/90) — 12 are decision-relevant (original exceeded 3.8 at 60% BEP). See fat_integrity_workbook.xlsx > 14_Coverage_Gap.

## Slide 7
6. 60% BEP — Off-Design Exceedances (Radial Thrust Region)
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
At 60% BEP (143 m³/h), the pump operates well below BEP with significant radial thrust and hydraulic recirculation. This is expected to elevate vibration but the measured values substantially exceed VR-001.
Point | Original (mm/s) | Retest (mm/s) | Limit | Margin | Status
PMP_DE_H | 3.90 | 3.40 | 3.80 | -0.40 | PASS
PMP_DE_V | 3.11 | 2.72 | 3.80 | -1.08 | PASS
PMP_DE_A | 2.52 | 2.28 | 3.80 | -1.52 | PASS
PMP_NDE_H | 4.91 | 4.16 | 3.80 | +0.36 | FAIL
PMP_NDE_V | 5.66 | 4.50 | 3.80 | +0.70 | FAIL
PMP_NDE_A | 3.77 | MISSING | 3.80 | n/a | NO DATA (D-09)
Assessment
▸ PMP_NDE_V retest 4.50 mm/s is +18.3% over limit — worst single exceedance
▸ PMP_NDE_H retest 4.16 mm/s is +9.5% over limit
▸ Both points improved vs original (PMP_NDE_V: 5.66→4.50, -20%) but remain non-compliant
▸ PMP_NDE_A retest data MISSING — VR-011 explicitly flags this as required evidence closure
▸ Spectral evidence at 60% shows elevated 1X (2.58 PMP_DE_H) and BPF (1.59) — recirculation effects
▸ PNDE_H 1X at 60% = 2.964 mm/s peak (SP-042) — FAILS VR-002
Mitigation: Operational Constraint
SAFEGUARD S-06: Minimum continuous flow enforced ≥ 80% BEP (≥191 m³/h) until field baseline confirms 60% BEP compliance with VR-001. This constrains operation above the radial-thrust region until field evidence closes the gap. Minimum continuous stable flow per datasheet is 70 m³/h — safeguard raises this to 191 m³/h pending verification.

## Slide 8
7. Spectral Events — Discrete Component Compliance (VR-002)
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
Event | Point | Flow | Freq | Order | Peak mm/s | Limit | Status
SP-011 | PMP_DE_H | 110% | 298.0 | BPF(6X) | 2.964 | 2.50 | FAIL +18.6%
SP-008 | PMP_DE_H | 110% | 49.7 | 1X | 2.850 | 2.50 | FAIL +14.0%
SP-042 | PNDE_H | 60% | 49.7 | 1X | 2.964 | 2.50 | FAIL +18.6%
SP-059 | MDE_A | 100% | 49.7 | 1X | 2.756 | 2.50 | FAIL +10.2%
SP-012 | PMP_DE_H | 110% | 347.7 | BPF+1X | 0.749 | 2.50 | PASS
SP-018 | PMP_DE_H | 90% | 298.0 | BPF(6X) | 0.426 | 2.50 | PASS
SP-001 | PMP_DE_H | 100% | 49.7 | 1X | 1.997 | 2.50 | PASS
VR-002 Summary
▸ Total spectral events: 62
▸ Compliant (≤ 2.5): 57
▸ Non-compliant (> 2.5): 5
▸ Highest peak: 2.964 mm/s
▸ Concentration: 110% and 60% BEP
Spectral Pattern Analysis
▸ BPF at 110% BEP (SP-011, 2.964 mm/s peak) is the highest discrete component — indicates volute/impeller interaction at high flow. Sidebands (BPF±1X) are modulated, suggesting cavitation or turbulence at volute tongue.
▸ 1X at 110% BEP (SP-008, 2.85 mm/s) elevated vs 100% (SP-001, 2.00 mm/s) — increased radial load from off-BEP hydraulic forces. 2X at 110% (SP-009, 1.70 mm/s) suggests misalignment indicator under load.
▸ At 90% BEP (near BEP at 238.5 m³/h), all spectral components are minimal — 1X=1.51, BPF=0.43 — confirming optimal hydraulic balance at design point.
▸ At 60% BEP, 1X and 2X elevated across all pump points — consistent with radial thrust from recirculation. PNDE_H 1X (SP-042, 2.964 mm/s peak) FAILS VR-002.
▸ Motor axial (MDE_A) 1X at 100% (SP-059, 2.756 mm/s peak) — monitor for thrust bearing wear and angular misalignment. 2X axial (SP-060, 1.17) supports angular misalignment indicator.

## Slide 9
8. Transient Analysis — Run-Up & Coast-Down
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
Chart: Vibration vs Speed (PMP_DE_H)
| 0.0 | 151.0 | 302.0 | 453.0 | 604.1 | 755.1 | 906.1 | 1057.1 | 1208.1 | 1359.1 | 1510.1 | 1661.1 | 1812.2 | 1963.2 | 2114.2 | 2265.2 | 2416.2 | 2567.2 | 2718.2 | 2818.9 | 2899.5 | 2939.7 | 2969.9 | 2980.0 | 2980.0 | 2980.0 | 2980.0
Run-Up | 0.021 | 0.083 | 0.156 | 0.25 | 0.395 | 0.541 | 0.738 | 0.926 | 1.186 | 1.435 | 1.789 | 2.09 | 2.444 | 2.787 | 2.517 | 2.267 | 2.402 | 2.621 | 2.818 | 2.933 | 2.891 | 2.922 | 2.954 | 2.964 | 2.964 | 2.954 | 2.964
Coast-Down | 2.964 | 2.902 | 2.787 | 2.652 | 2.506 | 2.371 | 2.236 | 2.475 | 2.829 | 2.402 | 1.924 | 1.581 | 1.258 | 0.978 | 0.749 | 0.562 | 0.406 | 0.281 | 0.187 | 0.114 | 0.062 | 0.021
Derived Metrics
▸ Rated speed: 2980 RPM
▸ Steady-state vib: 2.964 mm/s RMS
▸ Resonance band: 1812 - 1963 RPM
▸ Resonance peak: ~2.83 mm/s RMS
▸ Amplification factor: ~1.18 (modest)
▸ Separation margin: 34.1%
▸ Coast-down time: 52 seconds
▸ Phase tracking: smooth, coherent
▸ Assessment: well-damped, single resonance below rated — acceptable for rigid-mount centrifugal pump
API 610 Guidance
API 610 requires ≥ 20% separation margin for damped critical speeds below operating speed. Observed 34% separation exceeds this. Amplification factor < 2.0 confirms well-damped system. Phase progression through resonance is coherent — no abrupt shift indicating structural looseness.

## Slide 10
9. Sister Pump Baseline — P-7402B Field Reference
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
Chart: P-7402B Field Trend — PDE_H at ~95% BEP
| Jul-25 580h | Oct-25 2720h | Jan-26 4980h | Apr-26 6940h | May-26 7920h | Jun-26 8040h | Sep-26 10560h | Dec-26 12840h
P-7402B PDE_H (mm/s RMS) | 1.45 | 1.48 | 1.52 | 1.68 | 2.35 | 1.38 | 1.55 | 1.72
VR-001 Limit | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8
P-7402B History
▸ Commissioned 2025-06-20, identical PWRI-220
▸ Location: Cooling Tower CT-3, rigid mount
▸ Current hours: 12,840 at 2026-12-10 survey
▸ DE bearing failure at 7,920 hrs (2026-05-28)
▸ Root cause: water ingress via breather → contaminated lubricant → inner race spalling
▸ WO-2026-0847: bearing + seals replaced (18 hrs)
▸ WO-2026-1103: upgraded desiccant breather fitted
▸ Post-repair baseline restored to 1.38 mm/s
Comparison: P-7402A Retest (90% BEP) vs P-7402B Field (95% BEP)
Point | P-7402A Retest | P-7402B Field | Delta | Implication
PMP_DE_H | 1.999 | 1.72 | +0.28 | A higher — residual imbalance or hydraulic signature
PMP_DE_V | 1.654 | 1.38 | +0.27 | A higher — consistent pattern
PMP_DE_A | 1.495 | 1.25 | +0.25 | A higher
PMP_NDE_H | 1.739 | 1.51 | +0.23 | A higher — bearing load signature
PMP_NDE_V | 1.453 | 1.22 | +0.23 | A higher
PMP_NDE_A | 1.317 | 1.08 | +0.24 | A higher — thrust bearing load

## Slide 11
10. Unresolved Evidence & Discrepancy Log
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
ID | Category | Description | Impact | Closure
D-01 | Exceedance | 110% PMP_DE_H 3.89 > 3.8 (+2.4%) | VR-001 non-compliance at overload | Field re-verification (S-01)
D-02 | Exceedance | 60% PMP_NDE_H 4.16 > 3.8 (+9.5%) | VR-001 non-compliance at low flow | Min flow ≥80% BEP (S-06)
D-03 | Exceedance | 60% PMP_NDE_V 4.50 > 3.8 (+18.3%) | VR-001 non-compliance at low flow | Min flow ≥80% BEP (S-06)
D-04 | Spectral | BPF 110% 2.964 > 2.5 peak (+18.6%) | VR-002 non-compliance | Field acoustic survey (S-09)
D-05 | Spectral | 1X 110% 2.85 > 2.5 peak (+14%) | VR-002 non-compliance | Field re-verification (S-01)
D-06 | Coverage (info) | 80% BEP not in retest (not required by VR-003) | No comparison at 80%; not a compliance gap | Field baseline (S-01)
D-07 | Coverage | DRV_NDE missing at 110% (3 pts) | Driver NDE unverified at overload | Field route (S-01)
D-08 | Coverage | All DRV missing at 90% (6 pts) | Driver unverified near BEP | Field route (S-01)
D-09 | Coverage | DRV+PMP_NDE_A missing at 60% | Thrust bearing assessment incomplete | Field route (S-01)
D-10 | Evidence | Contract limit 'submitted' not 'verified' | Governing rule authority uncertain | Board confirm (A-01)
D-11 | Evidence | Baseplate 'contradicted' 0.08 mm/m | Installation flatness unknown | Field re-survey (S-03)
D-12 | Evidence | Shaft runout 'contradicted' 0.021 mm | Evidence state questioned | Independent check (S-04)
D-13 | Evidence | Alignment 'field-verification-required' | Hot alignment unknown | Hot check (S-02)
D-14 | Sister | P-7402B bearing failure (water ingress) | Service risk indicator | Breather upgrade (S-05)
D-15 | Sister | P-7402A ~0.25 mm/s higher than P-7402B | Baseline gap | Field trending (S-08)

## Slide 12
11. Uncertainty & Sensitivity Analysis
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
Key Uncertainties
▸ Retest Coverage
Only 32 of 180 required combinations captured (17.8%). DRV incomplete at 60/80/90/110; PMP missing at 60/80/90 (28 combinations, workbook 14_Coverage_Gap). Cannot fully characterize machine state.
▸ Contract Authority
ME-001/009/017 (3.8 mm/s limit) in 'submitted' state. If actual contract limit differs, disposition changes.
▸ Evidence States
6 'contradicted' + 6 'field-verification-required' items. Foundation and alignment unknowns could shift vibration by 0.5-1.0 mm/s in field.
▸ Sister Applicability
P-7402B at 12,840 hrs vs P-7402A at 0 hrs. Break-in effects, foundation differences, piping strain not accounted for.
▸ Process Conditions
FAT on water at 35°C. Field service is produced water — density, viscosity, gas content differ. Vibration may increase.
Sensitivity Scenarios
Scenario | 110% PMP_DE_H | Status | Trigger
Current retest | 3.89 mm/s | FAIL +2.4% | Baseline condition
+0.05 alignment degradation | ~3.94 mm/s | FAIL +3.7% | Hot alignment shift
+0.10 foundation/piping strain | ~3.99 mm/s | FAIL +5.0% | Typical field effect
+0.25 (sister-pump gap closure) | ~4.14 mm/s | FAIL +8.9% | Matches P-7402B field delta
Worst-case combined | ~4.29 mm/s | FAIL +12.9% | All adverse effects
If VR-000 (4.2) were governing | 3.89 mm/s | PASS | But VR-000 is superseded
Sensitivity Conclusion
The 110% BEP margin of only 0.09 mm/s is highly sensitive to field conditions. Any realistic degradation (alignment shift, foundation settling, piping strain, process fluid change) will push the 110% point further into non-compliance. This is why closure action C-11 (monitored 90-100% BEP commissioning run with hold points) and C-08 (approve commissioning alarm ~2.4 / trip ~3.5 mm/s RMS per 9_Thresholds) are non-negotiable. At 90-100% BEP, margins are 1.0-1.5 mm/s — robust.

## Slide 13
12. Commissioning Safeguards — 10 Mandatory Gates
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
Gate | Safeguard | Acceptance Criteria | Hold Point | Closes
S-01 | Field vibration baseline (full matrix) | All points ≤ VR-001 & VR-002 at 60/80/90/100/110% BEP | YES | D-01..D-09
S-02 | Hot alignment at operating temp | Per API 610 / vendor spec | YES | D-13
S-03 | Baseplate level re-verification | ≤ 0.05 mm/m post-grouting | YES | D-11
S-04 | Shaft runout independent check | ≤ 0.025 mm TIR (VR-006) | YES | D-12
S-05 | Desiccant breather upgrade | Per WO-2026-1103 configuration | YES | D-14
S-06 | Min continuous flow ≥ 80% BEP | ≥191 m³/h until S-01 passed | YES | D-02, D-03
S-07 | Alarm/trip setpoints applied | Per VR-009/VR-010 from field baseline | YES | Protection
S-08 | Intensified surveillance | Weekly × 1000 hrs then monthly | NO | D-15
S-09 | BPF trending at 110% BEP | BPF peak ≤ 2.5 or stable trend | NO | D-04
S-10 | Field shutdown threshold | Any point > 4.5 mm/s RMS → trip | YES | Risk mitigation
Hold-Point Sequence
Pre-startup (S-02, S-03, S-04, S-05): Mechanical installation verification. All must be CLOSED before first rotation. Startup (S-01, S-06, S-07): Field vibration baseline capture at all flow conditions. Minimum flow enforced until S-01 passes. Protection setpoints applied before sustained operation. Early life (S-08, S-09, S-10): Intensified surveillance with shutdown threshold at 4.5 mm/s RMS. BPF trending at 110% BEP to monitor volute/impeller interaction. Any hold-point failure triggers STOP and investigation. No bypass without board re-convening.

## Slide 14
13. Board Action & Sign-Off
P-7402A Release Board | fat_integrity_workbook.xlsx | CONFIDENTIAL
REQUESTED DISPOSITION: CONDITIONAL RELEASE of P-7402A for offshore commissioning Subject to 12 mandatory closure actions (C-01 through C-12) and 4 board actions (A-01 through A-04)
Board Actions
A-01
Confirm VR-001 (3.8 mm/s RMS, API 610 Table 8, effective 2026-01-01) is the governing contract limit. Verify ME-001/009/017 authority from purchase specification.
A-02
Accept 10 material exceptions (E-01 through E-10) with documented commissioning safeguards. Acknowledge residual risk at 60% and 110% BEP.
A-03
Authorize conditional release with closure actions C-01 through C-12 as mandatory hold-points. No bypass without board re-convening.
A-04
Confirm sister-pump learning applied: upgraded desiccant breather (per WO-2026-1103) fitted to P-7402A before first startup.
Sign-Off
Role | Action | Signature | Date
Rotating Equipment Reliability Lead | Prepared & Recommended |  | 
Project Engineer | Reviewed — Scope & Schedule |  | 
Maintenance Superintendent | Reviewed — Safeguard Resourcing |  | 
Technical Authority | Approved / Rejected / Conditional |  | 
Supporting documents: fat_integrity_workbook.xlsx (auditable, formula-driven) | equipment_evidence_ledger.csv | fat_retest_measurements.csv | fat_spectral_events.csv | fat_runup_coastdown.csv | sister_pump_field_baseline_P7402B.csv | vibration_acceptance_rule_matrix.csv | pump_specification_P7402A.xlsx